Local Government Initiative on Climate Change (LoGIC)

ANNUAL programme NARRATIVE progress report

REPORTING PERIOD: 1 january – 31 December 2022

| Programme Title & Project Number |  | Country, Locality(s), Priority Area(s) / Strategic Results |
| --- | --- | --- |
| Programme Title: Local Government Initiative on Climate Change (LoGIC) MPTF Office Project Reference Number: 00103800 |  | Country/Region: Bangladesh |
|  |  | Priority area/ strategic results: By 2026, more people, in particular, the most vulnerable and marginalized, have improved access to and utilization of quality, inclusive, gender- and shock-responsive, universal, and resilient social protection, social safety-net and basic social services. |
| Participating Organization(s) |  | Implementing Partners |
| United Nations Development Programme (UNDP) United Nations Capital Development Fund (UNCDF) |  | Local Government Division, Ministry of Local Government, Rural Development and Co-operatives |
| Programme/Project Cost (US$) |  | Programme Duration |
| Total approved Prodoc Budget: | 36,060,000 |  | Overall Duration (months) | 81 |
| MPTF/JP Total Contribution: | UNDP 10,597,339 UNCDF 6,112,573 TOTAL 16,709,912 |  | Start Date (dd.mm.yyyy) | October 2016 |
| Agency Core Contribution: | UNDP 300,000 UNCDF 300,000 |  | Original End Date (dd.mm.yyyy) | 30 June 2020 |
| Government Contribution | GoB 440,000 |  | Current End date(dd.mm.yyyy) | 30 June 2023 |
| Other Contribution -EU | UNDP 8,530,035 UNCDF 8,519,843 TOTAL 17,049,878 |  |  |  |
| TOTAL Project Budget in USD: | 36,060,000 |  |  |  |
| Programme Assessment/Review/Mid-Term Eval. |  | Report Submitted By |
| Assessment/Review - if applicable please attach Yes No Date: 31 Dec 2022 (attached) Mid-Term Evaluation Report–if applicable please attach Yes No Date: |  | Name: Stefan Liller Title: Resident Representative Participating Organization (Lead): UNDP Email address: stefan.liller@undp.org |

Acronyms and Abbreviations

ATM		Adaptation Tracking and Measuring

AWP		Annual Work Plan

BMD		Bangladesh Meteorological Department

CALO		Climate Adaptive Livelihood Options

CCA		Climate Change Adaptation

CFF		Climate Fiscal Framework

CMF		Community Mobilization Facilitator

CRA		Community Risk Assessments

CRF		Community Resilience Fund

CSO		Civil Society Organization

DDLG		Deputy Director Local Government

DEM		Digital Elevation Model

DMC		Disaster Management Committee

DPP		Development Project Proforma

DRR		Disaster Risk Reduction

EU			European Union

FYP		Five Year Plan

GCF		Green Climate Fund

GED		General Economics Division

GoB		Government of Bangladesh

HH-RRAP		Household Risk Reduction Action Plan

HDC		Hill District Council

LCFF		Local Climate Fiscal Framework

LDP		Local Development Plan

LGD		Local Government Division

LGI		Local Government Institution

LGSP		Local Government Strengthening Project

LoGIC		Local Government Initiative on Climate change

M&E		Monitoring and Evaluation

MIS		Management Information System

MoDMR		Ministry of Disaster Management and Relief

MOU		Memorandum of Understanding

MPTF		Multi Partner Trust Fund

NIM		National Implementation Modality

NPD		National Project Director

PBCRG		Performance Based Climate Resilience Grants

PIC			Project Implementation Committee

PMU		Programme Management Unit

PPE		Personal Protective Equipment

PSC		Project Steering Committee

RCP		Representative Concentration Pathways

RRAP		Risk Reduction Action Plan

SIDA		Swedish International Development Cooperation Agency

TBD		To Be Determined

UNCDF		United Nations Capital Development Fund

UNSDCF		United Nations Sustainable Development Cooperation Framework

UNDP		United Nations Development Programme

UNO		Upazila Nirbahi Officer

UP			Union Parishad

# Executive Summary

The Local Government Initiative on Climate Change (LoGIC) is a joint initiative of GOB, UNDP, UNCDF, EU and Sweden to support the needs of communities in 72 Unions in seven districts, which have been identified as the most climate-vulnerable locations of Bangladesh. In 2022, LoGIC resumed all interventions which were almost suspended due to Covid-19 induced lockdown since April 2020, and this Annual Progress Report confirms the maturation of the project interventions since its beginning in 2017.

LoGIC has established itself as a sustainable model for locally led adaptation and developed a systemic approach to deliver climate finance to the most vulnerable people and local governments with lower transaction costs and higher adaptation benefits. The project’s exemplary contributions to climate change adaptation in Bangladesh, referred to the National Adaptation Plan (NAP) and recognized in the Government’s Mujib Climate Prosperity Report 2030 that was presented at COP26. The locally led adaptation model of LoGIC is a proven business case for the LGD to scale-up nationally and showcase it as a global best practice model.

LoGIC provided grants and capacity building support to 1.38 million most vulnerable people (56% women) to create a climate-resilient pathway, and a cost-benefit analysis shows that 62% direct benefit and 38% co-benefit of LoGIC investment in community-level schemes.

With LoGIC support, 100,339 populations from 35,000 households in 72 Unions of 7 Districts across the country are becoming climate resilient with better incomes, health, and higher awareness of climate change adaptation through capacity building and grants support. LoGIC also supported poverty reduction by strengthening the climate-adaptive livelihoods of the households. LoGIC promotes market linkages and the financial inclusion of 35,000 climate vulnerable households, provided USD 9.72 million to beneficiaries as financial support to implement climate adaptive livelihoods and disbursed USD 7.91 million to 72 Union Parishads to implement 639 climate adaptive community level schemes.

LoGIC emphasizes means and opportunities by which local government institutions can strengthen their capacities, systems, and processes in risk-informed planning and budgeting. LoGIC implemented the project in a highly participatory manner, engaging stakeholders at all different levels, consulted to ensure the climate resilient actions are implemented following the best approach and methods considering the risks and challenges in the local contexts and collected local stakeholder feedback on project implementation through different types of meetings, workshops, studies and addressed with their involvement for better project results.

In 2022, the successes of LoGIC were largely due to the tremendous commitment of the LoGIC team. The project is well on track to achieving the results and objectives that were set out in the beginning.

# Purpose

## I. Objectives

One of the outcomes of the United Nations Sustainable Development Cooperation Framework (UNSDCF) and Country Programme Document (CPD) for Bangladesh is "By 2026, more people in Bangladesh, particularly the most vulnerable and marginalized from all gender and social groups and those from lagging districts, benefit from sustainable livelihoods and decent work opportunities resulting from responsible, inclusive, sustainable, green and equitable economic development." In alignment with this outcome, the overall objective of the LoGIC is "Improved and inclusive local level planning, and increased funding for community based CCA-DRR solutions, supported by a strengthened financing mechanism".

The three key output level results envisaged to be achieved by LoGIC are:

- Strengthened capacity of local governments, households and other local stakeholders to develop local plans that integrate CCA-DRR solutions.

- Established financing mechanism to fund local governments and communities for implementing climate change adaptation measures.

- Experience and evidence inform and contribute to further improvements in policies and practices for UPs and national systems in relation to CCA.

## II. Results

- Key Achievements:

LoGIC interventions reduced climate change vulnerabilities for 1.38M people (56% women) from 322,486 households. Over 100,000 people from 35,000 households have become climate resilient, with improved income, health, and increased awareness of climate change adaptation. LoGIC Introduced sheep insurance to support 4,634 vulnerable households in enhancing livestock resilience and protection.

LoGIC took an ecosystem-based approach and implemented 169 nature-based community schemes that helped 213,187 people who are susceptible to climate change. LoGIC promoted the use of 932 kW of green energy through 100 nature-based community-level schemes.

A Climate Vulnerability Index has been created at the union level & utilized by the Local Government Division to allocate resources to local government institutions for climate adaptation initiatives.	LoGIC has developed a local financing model to deliver climate finance to the most vulnerable people and LGIs with lower transaction costs & higher adaptation benefits.

The achievement in 2022 are given below:

- Total 35,000 CRF beneficiaries (99% women) were selected through grievance redress mechanism and they received training on climate adaptive livelihood options (CALO).

- A total of 247 ward-level climate smart cooperatives have been formed by 35,000 CRF beneficiaries to implement climate adaptive livelihood options (CALO). A total of 215 Ward level cooperatives have already been registered with dept. of cooperatives of Bangladesh.

- LoGIC designed and introduced Climate Adaptive Insurance (Sheep Insurance) to improve the resilience and safeguarding of the most vulnerable 4,634 households. 1,824 beneficiary households received insurance benefits in the reporting year.

- Newly elected 72 Union Parishads were provided training on climate change issues including positive and negative lists of investments, financial management, co-financing and execution of climate adaptive PBCRG schemes.

- LoGIC organized three workshops at the Union level in Khulna on nature-based solutions to climate change adaptation. Community beneficiaries, UP bodies, CSOs, officials of the forest department, and project staff participated in the workshops.

- LoGIC trained 388 participants of 15 Union Parishads on social audit. UP Chair, Members, CSO representatives and project front line staff attended the training. A social audit team was formed in each of the 15 Union.

- LoGIC used the popular social media platform in Bangladesh, Facebook, to circulate project outcomes and activities through social media mobilization. Throughout the year, the page reached 203,386 audience members and engaged them in discussions on climate change.

- Two quarterly newsletters or E-bulletins were disseminated to all stakeholders at district and national levels, providing information on the project’s major highlights, events, achievements and learnings.

- USD 7.91 million (Inception to Dec 2022) disbursed to 72 UPs as PBCRG to implement 852 climate-resilient community-level schemes.

- LoGIC ensured safe drinking water for the most climate vulnerable 27,000 households (116,000 people) in salinity prone area through installation of 74 safe water system (RWHS/PSF/Tube well).

- USD 9.72 million (Inception to Dec 2022) disbursed to 35,000 selected beneficiaries as CRF. 58% of the beneficiaries are implementing Climate Adaptive Livelihood Options (CALO), 43% have gained economic benefit from CALO.

- 61% of LoGIC beneficiaries (Out of 35,000) in the practice of savings and mobilized USD 1 million in their implementation groups. The beneficiaries are using their own money in addition to project support to scale up and sustain their climate-resilient livelihoods.

- To facilitate the inclusion of CRF beneficiaries into the formal banking system, and their access to Mobile Financial Services (MFS) LoGIC ensured the opening of a mobile wallet of 35,000 beneficiaries.

- LoGIC has created a Climate Vulnerability Index (CVI) at the Union level. It will enable the Government to create a national database that maps the country's climate vulnerability and adaptive capacities, which can be used for climate vulnerability-based development budget allocation in the local government institutions.

- To institutionalize the locally-led adaptation planning and financing, the Local Climate Financing Framework (LCFF) model is developed based on LoGIC experience. LoGIC shared the LCFF to Local Government Division (LGD) to ensure a policy provision for LCFF in the revised Climate Financing Framework (CFF).

- LoGIC strengthened the network and linkages between 35,000 CRF beneficiaries and 19 Upazila level govt. line department officials i.e. livestock, fisheries, and agriculture departments enhanced their support to the vulnerable households in climate resilient actions.

- LoGIC project commissioned and managed mid-term evaluation. The mid-term evaluation analysed LoGIC progress thus far to provide information and recommendations that are useful and relevant to support evidence-based program management and broader strategic decision-making.

- To evaluate the profitability analysis and assess the perception index of climate change adaptation interventions LoGIC project conducted a study on cost-benefit analysis of community-level climate change adaptation-linked schemes. The study reveals 62% direct benefit and 38% co-benefit of LoGIC investment in community level schemes.

- The locally led adaptation model of LoGIC is a proven business case for the Local Government Division (LGD) to scale up nationally and showcase as a global best practice model. The project’s exemplary contributions to climate change adaptation in Bangladesh referred to the National Adaptation Plan (NAP) and recognized in the Government’s Mujib Climate Prosperity Report 2030. LoGIC project organized a side event in COP27 to share its learning and the model to the global audiences.

CAPACITY STRENGTHENING

LoGIC envisioned forming cooperatives involving the Climate Resilient Fund (CRF) beneficiaries with a legal organizational structure. With the facilitation of LoGIC project, 247 Climate Smart Cooperative Society are formed to enhance the climate adaptive livelihood for the climate vulnerable people of LoGIC working areas. These cooperatives have already been registered under the Department of Cooperatives. This will help CRF beneficiaries to deposit a certain amount of periodic savings (61% of beneficiaries are in savings practice now). To form the cooperatives all beneficiaries of a Upazila came under the same umbrella. The cooperatives of the CRF beneficiaries allow them to get access to financial institutions such as banks, capital markets etc. The cooperatives can be owner of the limited company to foster large scale investment of value chain of climate resilient livelihoods (Crab Hatchery, Crab Processing Plant, Sheep Breeding Plant, Sheep Meat Processing, Sunflower-Sesame-Mastered Oil Processing Plant, Dry Food Processing Plant, etc.). A total of 247 ward-level climate smart cooperatives have been formed by 35,000 CRF beneficiaries. Total 215 Ward level cooperatives have already been registered with dept. of cooperatives.

In 2022, 34,476 CRF beneficiaries received training on climate adaptive livelihood options (CALO). To ensure the capacity building on climate resilient means of livelihoods for CRF beneficiaries and linkage with private sector actors for scalable business opportunities a partnership between LoGIC and BRAC has been signed.

81% beneficiary groups have knowledge and skill on CALO. But 53% of them are confident to implement CALO without support from LoGIC. It’s found less in Bhola (43%) and Barguna (46%). 50% beneficiaries can do the bank transactions by themselves and 47% can manage support from Union Parishads and/or Upazila line department officials to implement their CALO.

Newly elected 72 Union Parishads were provided training on climate change issues including positive and negative lists of investments, financial management, co-financing and execution of climate adaptive PBCRG schemes. LoGIC organized three workshops at the Union level in Khulna on nature-based solutions to climate change adaptation. Community beneficiaries, UP bodies, CSOs, officials of the forest department, and project staff participated in the workshops.

In 2022, 48 UPs updated their risk reduction action plans (RRAP) which were also integrated in the 5-years plan of UP. LoGIC trained 388 participants of 15 Union Parishads on social audit. UP Chair, Members, CSO representatives and project front line staff attended the training. A social audit team was formed in each of the 15 Union.

Provide mental health support to the climate change victims

An initiative was taken jointly by the LoGIC project and Moner Bondhu (An NGO) to address the psychological crisis brought about by the impacts of climate change for the people in the coastal belt.

An event was organised in Kamarkhola Union of Dacope Upazila under Khulna to mark World Mental Health Day, where nearly 50 people, including men, women and adolescents were brought together to raise awareness about the correlation between climate change and mental wellbeing, as well as provide strategies to the victims to build psycho-social resilience in their day-to-day struggle with the impacts due to natural disasters. Climate change poses serious mental and emotional health risks, from distress to anxiety, post-traumatic stress disorder, depression, grief, and suicidal behavior.

Financing Mechanism

Community Resilient Fund (CRF): LoGIC support to Household level adaptation

LoGIC provided financial support (CRF) to 35,000 selected beneficiaries (99% women) who are implementing Climate Adaptive Livelihood Options (CALO) and 80% of beneficiaries (1st & 2nd Round) has gained positive economic benefits. The financial security gained through these initiatives will ensure that vulnerable households are cushioned against shocks and disasters. CRF beneficiaries (1st & 2nd) are practicing 20 types of CALO. A maximum 25% are implementing sheep rearing and 19% are duck rearing, both following individual approaches. In groups, mainly fish (13%) & agriculture (16%) based CALO are in practice.

The economic benefit includes more income than investment (1>1). The benefit may be deposited to their bank account or be consumed. If beneficiaries have a loss in one cycle but gained more profit in the next cycle and that is more than the loss in the last cycle then the beneficiary group is considered as they have gained economic profit. Beneficiaries from Kurigram reported to gain 100% profit from practiced CALO whereas Bhola only obtained 23%. Patuakhali also showed a low benefit of 66% but other 5 districts displayed a decent percentage of profit.

The return of investment (ROI) of CRF money is very poor in Kurigram (1%) and Sunamganj (2%). In these Districts, the beneficiaries withdraw CRF money from their account but at the end of the CALO cycle they don’t re-deposit the capital or profit to the account rather they consumed all. In some cases, the beneficiaries keep the money with them and invest them in the next CALO or cycle. Patuakhali (15%) and Bagerhat (19%) have improved a little. The ROI is high in Bhola and Barguna.

The source of income has been diversified among the CRF beneficiaries due to CALO. Now 26% of beneficiaries have more than one source of income. HH average income has decreased in Dec 2022 than last quarter. In August 2022 it was 9%. Seasonal migration has decreased and household savings has been increased. Out of 35,000 CRF beneficiaries, 43% have gained benefit from CALO, but among the old beneficiaries (17,000) this rate is high, 80%. The new beneficiaries have started their CALO very recently and haven’t reached the stage of gaining. 12% groups have lost capital due to climatic disaster or Covid19.

Performance-Based Climate Resilient Grant (PBCRG): LoGIC support to Union Parishads for Climate Change Adaptation Actions

LoGIC provided grant support to 72 UPs to implement 216 climate-resilient schemes. All schemes O&M committees are formed and 70% of them are trained on their roles and responsibilities to ensure sustainability. PBCRG has been invested in a wide range of potential investments in the following key intervention areas in seven districts, each with its own set of socioeconomic, environmental, and climate-related challenges. In the reporting year LoGIC provided support to implement the following climate change adaptation schemes:

- Installed 68 climate-resilient safe water and sanitation solutions;

- Promoted climate-adaptive and environment-friendly irrigation systems and agricultural practices through 38 canal re-excavation and 16 solar-powered irrigation system;

- Implemented 5 vetiver grass plantation and 4 swamp forest schemes to demonstrate nature-based solutions to climate change adaptation;

- Installed 14 improved WASH facilities in cyclone & flood shelters flood resilient tube well in climate-vulnerable areas with a special focus on women’s needs;

- Improving access to cyclone shelters, flood shelters, and killas in climate-vulnerable areas through the construction of 58 schemes on roads and bridges;

- Reduced the impacts of climate change-induced floods and waterlogging with 13 schemes of culverts, drains, flood protection walls and guide walls;

- 16 schemes for improving the absorptive, adaptive, and transformative capacity of vulnerable communities;

- Enhanced the safety of vulnerable people from climate change-related extreme weather events by providing safety equipment to sea-going fishing boats and lightning/flood shelter).

LoGIC designed a unique model of community level safe drinking water support system from rainwater harvesting. This is a nature-based rainwater harvesting system using biodegradable and sustainable microorganism protective bio bags, which is locally available or the user households can make it by themselves.  With the PBCRG fund 5 schemes on vetiver plantation for nature-based slope protection, 3 schemes on mangrove plantation, 4 schemes on swamp plantation to protect riverbank erosion and different natural calamities have been implemented in Khulna, Kurigram and Sunamganj District. These schemes are very new in the area.

Policy Advocacy

LoGIC has created a Climate Vulnerability Index (CVI) at the Union level. It will enable the Government to create a national database that maps the country's climate vulnerability and adaptive capacities, which can be used for climate vulnerability-based development budget allocation in the local government institutions.

To institutionalize the locally-led adaptation planning and financing, the Local Climate Financing Framework (LCFF) model is developed based on LoGIC experience. LoGIC shared the LCFF with Local Government Division (LGD) to ensure a policy provision for LCFF in the revised Climate Financing Framework (CFF). LoGIC also strengthened the network and linkages between 35,000 CRF beneficiaries and 19 Upazila-level govt. line department officials i.e. livestock, fisheries, and agriculture departments to support the vulnerable households in climate resilient actions.

A workshop on 'Reporting on Climate Change and Climate Finance' was organized in Khulna District to engage media workers in information-based climate change-related reporting. Twenty-one media personnel participated in the workshop.

LoGIC project commissioned and managed mid-term evaluation by external organization. The mid-term evaluation analyzed LoGIC’s progress thus far to provide information and recommendations that are useful and relevant to support evidence-based program management and broader strategic decision-making. The evaluation report has been published and shared with the stakeholders.

To evaluate the profitability analysis and assess the perception index of climate change adaptation interventions, LoGIC project conducted a study on cost-benefit analysis of community-level climate change adaptation-linked schemes. The study shows that the estimated overall direct benefit and co-benefit are 62% and 38% respectively in terms of all implemented climate change adaptation schemes. The calculated Benefit Cost Ratio is 3.91 for the total benefit consisting of direct (2.41) & co-benefit (1.50). Adaptive water & sanitation solutions get the highest rank considering total benefit.

The study recommends the implementation of more climate change adaptation plans so that residents of climate-vulnerable areas can easily maintain their way of life. The infrastructures must, however, be periodically monitored and, if necessary, maintained if they are to be used more widely and sustainably, given that they are located in relatively climate-vulnerable areas and regions.

The locally led adaptation model of LoGIC is a proven business case for the Local Government Division (LGD) to scale up nationally and showcase as a global best practice model. The project’s exemplary contributions to climate change adaptation in Bangladesh, referred to the National Adaptation Plan (NAP) and recognized in the Government’s Mujib Climate Prosperity Report 2030 that was presented at COP26.

LoGIC project hosted a side event on “Locally-Led Adaptation (LLA) Initiatives through Local Governance and Innovative Climate Financing” in the Bangladesh Pavilion at COP27. The event presented how the LoGIC project promotes LLA through innovative financing and adaptation solutions that increase the resilience of the most climate-vulnerable communities across Bangladesh. Overall, the side event successfully shared LoGIC’s successes and learnings with an international audience and contributed to the broader discussions on adaptation and climate finance held at COP27.

Engaging the youth in climate change adaptation actions

LoGIC developed a youth strategy to engage them in Climate Change Adaptation (CCA) linked actions in the project working areas. Completed mapping and identified 8,872 youth from vulnerable communities and project beneficiaries to engage them with project activities including, social auditing and adaptation enterprise; and promotion of nature-based solution.

- Key challenges and mitigation measures:

- In certain regions, households receiving CRF from the LoGIC may decline to engage in group activities or work outside their homes. This may be attributed to a traditional mindset of relying on relief aid and a conservative outlook. Such beneficiaries often perceive the monetary support provided by the government as a form of relief and tend to allocate it according to their individual needs. LoGIC increased follow-up and capacity building of the beneficiaries to overcome the challenges.

- Due to climate change, large-scale rainwater harvesting systems (RWHS) are facing challenges. According to the Bangladesh Meteorological Department, average rainfall is decreasing every year. We should build relatively low-capacity RWHS by using existing school or mosque roofs.

- The male mindset presents a challenge to allowing females to travel and work for their livelihood. Additionally, male representatives in Union Parishads are often reluctant to consult and listen to women when it comes to planning and implementation. To address this issue, LoGIC is working to minimize the gender gap by discussing it with male household members and Union Parishad members.

- LoGIC CRF beneficiaries have been reluctant to access formal banking services due to their mistrust, lack of financial literacy, and the long distances they must travel. Although agent banking is a way to extend a bank's presence into remote villages, these services are currently only available up to the Upazila level.

- The CRF women beneficiaries are increasingly engaging in climate-adaptive livelihood activities, such as agriculture. However, they are also responsible for managing all household duties, commonly referred to as "women's work". As a result, these women are overburdened and severely limited in time. To promote household resilience, it is crucial to ensure an equitable distribution of both agricultural and household duties.

- Sustaining the LoGIC results and impacts of climate change adaptation interventions presents a challenge due to the dynamic nature of climate change impacts, which are influenced by localized factors. As a result, effective solutions are context-specific and time-limited. LoGIC has already updated the indicative list of climate-adaptive livelihood options (CALO) to make it contextual.

- Lessons Learned:

- Union Parishads and vulnerable communities are more familiar with disaster management actions rather than climate change adaptation (CCA) solutions. LoGIC’s participatory and technology-based intervention has helped them to understand climate change and how to take actions for climate change adaptation.

- The development of climate risk-informed Local Development Plans (LDP) by the Union Parishads requires significant capacity building support. LoGIC emphasizes means and opportunities by which Union Parishad can strengthen their capacities, systems and processes in adaptation planning and budgeting.

- There remains a preference among stakeholders of traditional development approaches and livelihood options that offer shorter-term solutions in contrast to climate adaptation interventions that offer longer-term solutions to reoccurring climate-induced challenges. More awareness raising and capacity-building is needed to change this perception.

- LoGIC has developed and utilized a participatory and technology-based beneficiary selection process, which enabled the project to select the most climate-vulnerable households, significantly reducing community grievances. The GoB can capitalize on this mechanism for other grants and safety-net programs.

- Integrating a top-up method into the bottom-up approach has enabled innovation and dissemination of knowledge among the marginalized population and has made the project more comprehensive and holistic.

- A more in-depth understanding of livelihoods of beneficiaries will be useful for the project to support them in their immediate, intermediate, and long-term strategy for achieving climate-resilient livelihood pathways.

- The project needs to develop effective ways to remove the practical and strategic barriers to the take up of CALOs, such as the risk of beneficiaries repurposing the CRF to respond to other challenges such as the COVID-19 pandemic, cyclone, flood, or other emergency responses. This would take away the purpose of the climate change project. Safeguarding CALOs and ensuring close monitoring may minimize the risks.

- There is an inequity in the CRF allocation, some people are receiving a substantial amount of financial assistance, while others are not receiving any at all. This could be addressed by creating different classes of eligible beneficiaries, each of which will receive different amounts and types of support.

- Way Forward

The current phase of LoGIC will end on 30th June 2023. The 6th Project Steering Committee (PSC) meeting suggested a new phase on a larger scale with possible funding sources from Development Partners (DPs) and the Green Climate Fund (GCF). Planning and designing the new phase in alignment with GCF will require significant time, resulting in a gap between the two and may impact the critical investments that the LoGIC project has made over the last five years. Therefore, the current project period is proposed to be extended with top-up support from DPs. The proposed extension duration is two years, from July 2023 to June 2025. The Embassy of Denmark has expressed interest in joining as a Development Partner (DP) of LoGIC in this extension and the next phases. The DPs have indicated a top-up of the existing LoGIC budget, including expanding the working areas into two new climate-vulnerable districts (Bandarban & Naogaon) from two climate-stress areas according to the climate vulnerable index (CVI) matrix and climate vulnerability. During the extension period, LoGIC will emphasize impact, sustainability of results, resource mobilization, and proposal development for the new phase with GCF to support the transformation of the LoGIC model as per the directive of the Honourable Prime Minister of Bangladesh as SMART Bangladesh.

The LoGIC team has developed a roadmap and is working on the GCF proposal development. The GCF concept note will be prepared by June 2023, and the full funding proposal will be submitted to GCF by September 2023. LoGIC's next phase is proposed to start on 1st July 2025, and end on 30th June 2030, and will directly increase the adaptive capacities of one million climate-vulnerable households (4.1 million indirect beneficiaries) across 300 Unions of 120 Upazila in 33 Districts. The project's new phase will work in six NAP climate-stress areas: Chattogram Hill Tracts (CHT); Drought-prone and Barind Area (DBA); River, floodplain, and erosion-prone area (FPE); Haor and flash floods area (HFF), Southeast and eastern coastal area (SEE); Southwestern coastal area and Sundarbans (SWM).

- Risk and Issue Management:

| Sl. | Project Risk This is mandatory. Please add project risks which your project has identified during the reporting period. | Likelihood (High/ Moderate/Low) | Mitigation Measure Each mitigation measure should respond to the project risk in the left column. |
| --- | --- | --- | --- |
| 1 | GoB staff positions related to the project remain vacant and Changes in UP political leadership may affect project delivery. | Low | Flexibility in the budget for additional capacity building support in case of change in UP leadership. |
| 2 | Risk of non-transformative resilience of CRF beneficiaries due to the fact that a year-round calendar for seasonal and continuous adaptation of their livelihoods is available. | Moderate | A yearlong district wise climate adaptive livelihood seasonal calendar was developed and skill transfer to the CRF beneficiaries was ensured. |
| 3 | Risk of the high scarcity of safe drinking water in the coastal areas of LoGIC project. | Moderate | Supply drinking water by relevant authorities and installation of water treatment plant with PBCRG support. |
| 4 | Risk of damaging the CRF livelihood initiatives due to flood and waterlogging | Moderate | Ensure early harvest of crops and necessary protection measures to fish and livestock. |
| 5 | Thundering is a risk for field implementation in the haor areas of Sunamganj. | Moderate | Beneficiaries and CMFs are suggested to avoid open spaces or electric pole and move to safe places during the thunderstorm. |
| 6 | Fiduciary risks of re-purposing the CRF by the project beneficiaries to meet cyclone & other emergency responses. | Moderate | Safeguarding climate adaptive livelihood options and ensure close monitoring. |
| 7 | Risk of slow progress of project activities due to Union Parishad election. | Moderate | Maintain careful relationship with UPs and involve DDLG and UNOs in decision making and implementation. |

- Partnership

Partnership with BRAC for capacity building of CRF beneficiaries

To ensure the capacity building on climate resilient means of livelihoods for CRF beneficiaries and linkage with private sector actors for scalable business opportunities a partnership between LoGIC and BRAC has been built. BRAC has developed 17 training modules on climate adaptive livelihoods (CALO) which have is support scalable business opportunities. The partnership is to provide training on most feasible adaptive livelihood and economically feasible adaptive livelihood options to 53,000 CRF beneficiaries.

Partnership with PCC & MEC to strengthen market linkage & financial inclusion of CRF beneficiaries

Financial inclusion of the most climate vulnerable people, especially women is one of the key priorities of the new strategy for low carbon climate resilient pro-vulnerable development. To establish market linkage & financial inclusion climate vulnerable households of CRF beneficiaries, LoGIC have made a partnership with Population Crisis Control and Mass Education Committee (PCC & MEC). The organization is providing support to facilitate the opening of individual and group bank accounts of newly selected 18,000 CRF beneficiaries, strengthen 35,000 beneficiaries’ capacity and understanding of access to financial resources, mobile wallet opening, services & markets and establishment of market linkage and value chain for the 2013 beneficiary groups of LoGIC for their resilient livelihood products.

Partnership with BUET and CNRS to strengthen nature-based solutions as PBCRG schemes

Partnership is important to enhance effectiveness of resilience building efforts as it offers the opportunity of complementing existing knowledge, skills, capacity, and resources. Therefore, in 2022 the LoGIC project entered into partnerships with Bangladesh University of Engineering Technology (BUET) and Center for Natural Resources Studies (CNRS) to designing and implementing certain PBCRG schemes that provide nature-based solutions to some climate change induced hazards.

The LoGIC project has partnered up with the BUET to transfer the technology of reducing soil erosion using vetiver grass to the local government. Under the provision of the partnership Professor Dr. Mohammad Shariful Islam, Department of Civil Engineering, BUET is providing necessary technical support to the LoGIC project to demonstrate vetiver-based slope protection schemes.

On the other hand, CNRS worked closely with the Union Parishads for mangrove plantations for swamp afforestation. Mangrove plantation has been done to prevent the damaging impact of cyclone and tidal surge, and the swamp forest will protect human settlements from eroding effect of flood and flash flood.

The LoGIC Project expects that the partnerships will act as key driving force for the successful implementation of the mentioned nature-based solutions.

Monitoring & Evaluation

The LoGIC M&E system plays an essential function for project implementation and programmatic improvement, providing valuable information on program targets and periodic progress, contributing to the overall achievement of the project’s goals. The main objective of LoGIC M&E system is to facilitate the project management staff to:

- Ensure operational activities are planned and implemented on time and aligned with the project’s overall objective.

- Establish a learning environment, identify potential shortfalls in the expected performance, and share successes.

- Develop appropriate remedial actions.

Monitoring

LoGIC Monitoring system has been established on project’s Log frame and Result Framework. The process emphasis on real-time feedback, more rigorous data collection, and quantifiable results, the spread and use of Information and Communication Technologies (ICT). Tab based data collection is one of the technologies LoGIC adopted for M&E. Visualizations of real time collected data in interactive dashboards help project management arrive at the right conclusions about programme implementation. LoGIC also used a virtual monitoring system i.e., video calling, to monitor community-level activities. The gathered information was shared in virtual meetings attended by stakeholders such as DDLG, UNO, Chairman, UP and LoGIC-PMU.

The project has created and maintained its Management Information System (MIS) and monitoring databases to capture and track beneficiary, household, Union Parishad and intervention level data necessary to calculate values for all indicators tracked quarterly and annually. The data captured in the databases was used to analyse project outputs and outcomes across geographic locations and findings were shared with project management on a quarterly basis.

The Adaptation Tracking and Measuring (ATM) system is used to measure and monitor the climate adaptation and resilience progress of households and communities receiving support from the project. The ATM collects data from project-supported households every month against the set adaptation indicators. The project management has agreed on set standards for all project interventions. The LoGIC M&E system has prepared five process monitoring tools based on these set standards and conducted regular monitoring of sample interventions using the tools.

Evaluation

Cost benefit analysis of LoGIC funded community level schemes

To evaluate the profitability analysis and assess the perception index of climate change adaptation interventions LoGIC project conducted a study on cost-benefit analysis of community-level climate change adaptation-linked schemes. The study led by Professor Dr. Bazlul Haque Khondker of Dhaka University used participatory methods and collect both quantitative and qualitative information to assess the project achievement. The study reveals 62% direct benefit and 38% co-benefit of LoGIC investment in community level schemes.

Reporting

- To document the project’s progress and challenges, as well as showcase LoGIC’s achievements, the following reporting documents were drafted in 2022:

- Quarterly Progress Reports

- Quarterly MIS Reports

- Quarterly Monitoring Reports

- MPTF Report (for Sweden)

- Six-Monthly report (for Local Government Division, GOB)

- Annual Progress Report 2022 (for EU)

- Cross-cutting issues

- Climate change affects everyone, but not equally. Women are among the most vulnerable to climate change due to inequality, marginalization, poverty and access to livelihoods. For that, women are at the greatest risk of climate-related hazards. LoGIC showed good results on gender across all areas of work, it can do more, for example creating diversified livelihood options to increase household income to women’s economic empowerment. The project met significant progress in the performance indicators of the log frame for gender equality and the empowerment of women.

- LoGIC adopted a ‘gender transformative’ approach and is supporting the most vulnerable women who have not been covered under any other programs other than normal disaster relief provided. Moreover, the project is being implemented in the remotest and most climate-vulnerable areas of the country with target beneficiaries coming from most marginalized groups such as women-headed households, persons with disability, ethnic minority groups, and small/marginalized occupational groups. LoGIC’s commitment to gender equality is reflected in its beneficiaries. 99% of CRF grants recipients are climate-vulnerable women. In the reporting period, LoGIC trained the 34,953 vulnerable women on 23 types of climate adaptive livelihood options.  Now the women can take on climate adaptive livelihood options (CALOs), increasing their social and financial security, as well as their independence and agency within their communities.

- LoGIC also linked the women to Upazila level govt. line department officials, local government institutions and service providers, which promoted women’s leadership in resilience building in the climate-vulnerable community.

- To empower women, LoGIC provided training to 34,953 vulnerable women on climate adaptive livelihood options. LoGIC also linked the women to Upazila level govt. line department officials, local government institutions and service providers, which promoted women’s leadership in resilience building in the climate-vulnerable community.

- Women are adequately represented in the operations & management committee of 643 PBCRG funded schemes, Scheme Implementation Committee (SIC) & Scheme Supervision Committee (SSC), additionally the risk assessment of communities include the documentation of women’s involvement in the communities’ decision-making processes regarding the community-led adaptation project.

- Self-employment, more income, financial inclusion and regular linkages with government officials and local government institutions helped build the communities’ acceptance of beneficiary women as able and contributing members of the society.

- Qualitative assessment

During the reporting period, the UNDP & UNCDF country office, Project Management Unit (PMU) and District level staffs visited UPs and community to check progress and quality of the project interventions. PMU also supported to strengthen the coordination with stakeholders at local and national level.

Project developed activity-wise monitoring checklists to assess the progress and the quality of the implementation of PBCRG schemes and the capacity development of livelihood options for the CRF beneficiaries.

LoGIC has made partnerships with some organizations/institutions to ensure timely delivery of project interventions and quality achievements of the project results.

- LoGIC Exposure in Media

The Local Government Initiative on Climate Change (LoGIC) has maintained and effectively sustained communication and visibility throughout the year 2022. It has also projected all its development partners and internal-external stakeholders in this process of communication.

LoGIC project is utilizing the power of community radios in Kurigram, Bhola, Barguna and Bagerhat districts which was a continuation of last year’s campaign. It started with the objective to profile the issue of climate change and to highlight the sustainable solutions to climate change adaptation, by building knowledge and awareness within the community.

Quarterly newsletters or E-bulletins have been published and disseminated to all stakeholders at district and national levels, providing all the information on the project’s major highlights, events, achievements, learnings, report dissemination, media engagements, visits from local government representatives, and inaugurations of schemes. Photo documentation capturing project outcomes and processes has been used in multiple communication materials and reports. Additionally, online stories, blogs, human stories, and write ups contribute to highlighting the project’s progress and achievements. In the year 2022, many big events like joint mission (EU-Sweden-GoB-UNDP-UNCDF) to Bagerhat, field training, CRF data collection, and safety security equipment distribution took place and all the highlights from those events have been captured and showcased in these newsletters.

LoGIC has its own social media page on Facebook which is the most popular social media platform in Bangladesh, to circulate project outcomes and activities. It includes 4,390 followers till now. Throughout the year, the page has reached 203,386 audiences. This page is mainly containing video and success story content which were directly produced from the field. LoGIC Project is also making a strong presence on Twitter. The Twitter handle is called @LocalResilienc1 and is followed by Sweden Ambassador, Sweden Embassy, European Union in Bangladesh, Kyoko Yokosuka, Van Nyeguen, UNCDF Local, National Resilience Programme and more. The Twitter posts are updated regularly and tagged by UNDP for prolonging climate change issues, highlighting project outcomes and engaging people in discussions.

LoGIC’s outreach through its website is noteworthy as well. A total of 13 success stories have been posted in the website. In addition, recently the website has been updated and many dynamic features have been added to make it user friendly and to contain more issue focused content. It is regularly supervised and publishes new stories, events, photos and videos. It is basically a knowledge hub for both national and international people who are interested in climate change and adaptation-related issues and project related information.

Media Workshop

A workshop was organized on 30th August 2022 at Khulna on Reporting on Climate Change and Climate Finance where 21 media personnel participated. Participating in the discussion, the media representatives said that the southern part of the country is the most affected due to climate change. For this reason, the coastal area of ​​Khulna deserves to be given priority in the use of climate funds. Durable embankments should be constructed to stop the intrusion of saltwater in coastal areas. Transparency and accountability should be increased in the use of climate fund money. At the same time, the media workers should be assisted in providing correct and information-based news by providing detailed information about the ongoing development activities in this sector.

|  | Achieved Indicator Targets | Reasons for Variance with Planned Target | Source of Verification |
| --- | --- | --- | --- |
| Outcome 1 Indicator: % of 72 UPs that have incorporated climate change adaptation actions into their development plans (LDP). Baseline: 13.9% (Jan, 2018) Planned Annual Target: 100% | 100% UPs have incorporated climate change adaptation into their annual and five-year’s development plans through developing Risk Reduction Action Plan (RRAP). In 2022, Climate Change Adaptation (CCA) actions are integrated and streamlined through UP schemes. This year, 72 UPs planned 654 CCA linked schemes. | NA | Annual Progress Report 2022 |
| Indicator: % of 72 UP plans that have addressed the adaptation needs and priorities of vulnerable women and girls. Baseline: 6.9% (Jan, 2018) Planned Annual Target: 50% | 100% of UPs have prioritized adaptation needs and priorities of vulnerable women and girls. In 2022, 37% of the UP CCA linked schemes for climate change adaptation needs of vulnerable women and girls. | NA | Annual Progress Report 2022 |
| Indicator: % of UP that have established and are implementing the Climate Resilience Financing system. Baseline: 0% (Jan, 2018) Planned Annual Target: 80% | 100% of the UP established and implemented the PBCRG with their own financing and accounting system & supported CRF interventions with their administrative system. Integration of CCA in UP planning has significantly increased compared to the previous year, which is a significant progress to achieve the LoGIC objective- to establish a financial mechanism for climate resilient action at local level. | NA | Annual Progress Report 2022 |
| Indicator: % of 27 UPs that are allocating other resources to implementing CCA linked schemes. Baseline: 31.9% (Jan, 2018) Planned Annual Target: 70% | 42% of CCA linked/Climate resilience schemes funded by LGSP, ADP, OSR or other allocation. In 2022, the progress indicated 26% less from 2021. | NA | Annual Progress Report 2022 |
| Output 1 Indicator (1): % of women, poor and marginalized people that participate in the formulation of climate risk integrated LDPs Baseline: 1.3% (Reference: LoGIC Baseline Study 2018) Annual Target: 52% | 100% of the selected 35,000 CRF beneficiaries (99% women, 6% representative of marginal occupational group, 4% Persons with Disability-PWD and 1% indigenous people) participated in the household risk reduction action plan (HH-RRAP) developing process. | NA | Annual Progress Report 2022 |
| Indicator (2): % of target UPs that integrate CCA solutions into LDPs to support the most vulnerable households. Baseline: 31.9% (Reference: LoGIC Baseline Study 2018) Annual Target: 100% | 100% of targeted 72 UPs integrated climate change adaptation (CCA) solutions into the local development plans (LDP). LoGIC conducted a study to evaluate the profitability analysis of the community level climate change adaptation linked schemes supported by PBCRG. The study shows that the estimated overall direct benefit and co-benefit are 62% and 38% respectively in terms of all implemented climate change adaptation schemes. | NA | Annual Progress Report 2022 |
| Output 2 Indicator (1): % of 17,000 vulnerable households (women, poor and marginalized) who benefit from CCA finance. Baseline: 10% (National) Annual Target: 60% | 76% of CRF beneficiary households gained economic benefit from implementation of their climate adaptive livelihood options (CALO). In 2022, 100% of the beneficiaries completed their 1st CALO and 80% of them implemented 2nd CALO also. 37% of beneficiaries implemented 3rd CALO, which is high in Sunamganj, Khulna & Barguna. The diversity in CALO implementation is high in Sunamganj, Barguna and Kurigram, but lowest in Bhola. | NA | Annual Progress Report 2022 |
| Indicator (2): % of 72 UPs that secure funding to support CCA linked schemes based on their performance. Baseline: 0% (Reference: LoGIC Baseline Study 2018) Annual Target: 100% | 100% of 72 UPs have secured PBCRG funding to support CCA linked schemes based on their performance. In 2022, allocation was given to 72 UPs for selected 216 schemes. 72 UPs prepared 216 CCA linked schemes based on that allocation and received the PBCRG money. UP performance in CCA linked scheme implementation was considered to define the UP-wise PBCRG allocation. | NA | Annual Progress Report 2022 |
| Indicator (3): % of Open Budget sessions in 72 UPs that discussed CCA linked expenditure. Baseline: 6.9% (Reference: LoGIC Baseline Survey 2018) Annual Target: 100% | 100% of Open Budget sessions in 72 UPs that discussed CCA linked expenditure. In 2022, all the UPs organized open budget meeting. 37% of the participants were female. | NA | Annual Progress Report 2022 |
| Output 3 Indicator (1): The extent to which National Adaptation Plan (NAP) and 7th Five Year Plan (7FYP) integrate financing for local adaptation. Baseline: 0 (No) (Reference: LoGIC Baseline Study 2018) Annual Target: Yes (Scale 1-4) | The locally led adaptation model of LoGIC is a proven business case for the Local Government Division (LGD) to scale up nationally and showcase as a global best practice model. The project’s exemplary contributions to climate change adaptation in Bangladesh, referred to the National Adaptation Plan (NAP) and recognized in the Government’s Mujib Climate Prosperity Report 2030 that was presented at COP26. | NA | Annual Progress Report 2022 |
| Indicator (2): The extent to which local climate financing framework is integrated into the national Climate Financing Framework. Baseline: 0 (No) (Reference: LoGIC Baseline Study 2018) Annual Target: Yes (Scale 1-4) | Local Climate Financing Framework (LCFF) model is developed based on LoGIC experience. LoGIC shared the LCFF to Local Government Division (LGD) to ensure a policy provision for LCFF in the revised Climate Financing Framework (CFF). Once the LCFF model is recognized National Climate Financing Framework and tested, LGD with enhanced capacity will be able to scale up it to all vulnerable UPs. | NA | Annual Progress Report 2022 |

## Success stories:

UNLEASHING NEW OPPORTUNITIES FOR CLIMATE-VULNERABLE WOMEN THROUGH FINANCIAL INCLUSION

Khulna which is located in the southern coastal belt of Bangladesh was once renowned for its bumper lush golden rice harvests. With the rising climate calamities, unprecedented flash floods, increased rainfalls, salinity intrusion in water along with cyclones and hurricanes occurring at regular intervals- the lush golden rice paddies have turned into endless stretches of barren land. Residing in the Tildanga Union of Dacope Upazila, Aarti Sana (38) has been fighting an unfair battle with climate calamities.

This is the same for the majority of the coastal areas where its residents like Aarti and her family depend largely on natural resources for economic survival. As resources get depleted or destroyed due to climate calamities, so do their livelihoods which pushes them into deeper pockets of poverty.

“We are extremely fearful about taking any risks in agriculture, but we have no option other than agriculture,” she said.

Poor people like Aarti and her family who have little to no land are more vulnerable to such uncertainty, increasing their displacement potential. There are minimal resources or funding mechanisms available to pursue alternative livelihoods or generate income. To ensure that the most climate-vulnerable women have the necessary resources, finances and capacity to build their resilience against climate change, LoGIC has opened bank accounts for each individual beneficiary to permanently include them within a financing system. Additionally, the project is providing a Community Resilience Fund (CRF) to each of those individual bank accounts as start-up capital to alternate climate-adaptive livelihoods. Moreover, the beneficiaries are trained to utilize their bank accounts most efficiently, conduct transactions, and use existing financing mechanisms available at banks to strengthen their climate-adaptive business models even further moving forward.

Opening a bank account is a beginning of a new chapter for most of these women. This is not merely a bank account but an identity for them– the very first step to their empowerment and a mechanism to be resilient to climate calamities.

“I am the only one in my family who has a bank account. Every time I go to the bank, sign and deposit cheques, it fills my heart with pride and a sense of accomplishment, said Rikta Roy, bank account holder from Tildanga Union.

The beneficiaries are introduced to the many advantages of engaging into a formalized banking system by the support of the project. They are provided with training to conduct traditional and mobile wallet banking mechanisms such as bKash, Nagad etc. Through this long-term financial inclusion, the beneficiaries have access to credit profiling, long term bank loans for supporting alternative climate-adaptive livelihoods. Moreover, this long-term financial inclusion enables planning for future financial investments, unlocking a broad spectrum of business opportunities for these marginalized climate vulnerable women.

Financial inclusion not only equips these women to continue their fight against climate change impacts by developing alternative livelihood solutions, it also helps them to have better control and accountability of their finances. Moreover, this engagement opens up the doors to extensive possibilities of entrepreneurship, business planning and investment, beyond LoGIC projects’ tenure.

“Access to financial inclusion has brought a sense of reliance and security in our lives. Like previous times, we are not afraid to take risks in agriculture anymore,” said Nasima Begum, a resident of Sonatola village, Burirchor Union, in Barguna district and a beneficiary of CRF.

LoGIC’s unique model has gained the confidence of women like Nasima, Rikta and Aarti by including them in financial institutionalizations, enabling them to further scale up their climate-adaptive livelihood business development portfolio. By 2023, LoGIC aims to support about 4,00,000 vulnerable households in 72 unions of seven districts — Khulna, Sunamganj, Kurigram, Bagerhat, Barguna, Patuakhali and Bhola.

Lightning sheds provide a refuge as deadly storms increase in Bangladesh

During the monsoon season, intense periods of lashing rains and storming skies ensure that the seasonal wetlands or haor region of north-eastern Bangladesh are flooded to become vast bodies of freshwater. Then, the region becomes a magnet for wildlife and local farming communities looking to boost meagre incomes by fishing. But as global temperatures rise and thunderstorms become more frequent in this part of Asia, the broad water expanses are increasingly a death trap that exposes fishers and their families to frequent and deadly lightning strikes.

Frightened of thunderstorms, many residents of Rafinagar Union of Sunamganj district scaled back their movements and limited afterdark fishing sorties across the open water expanses during the monsoon season. Yet, they did not want to entirely abandon the fertile fishing grounds that boosted their incomes. Working with local government representatives, they found a way to adapt to their new reality with the construction of a series of ‘lightning sheds’ or refuges where people can shelter safely during a storm.

“Last year three people died in this haor in the rainy season because they did not find any shelter to survive,” said Shabana Khatun, wife of a fisherman in Mirzapur village of Rafinagar Union. “We have relatives but could not visit them because we were scared as it was not safe to visit them with kids and travel through this haor in the rainy season.”

“Now we can go without any fear as there is that lightning shed. The lightning shed make us feel safe in the haor, now men can earn more as they can do fishing at night,” she added.

Bangladesh has one of the highest rates of death by lightning on the planet with over three hundred recorded fatalities in any one year. As carbon emission build in the earth’s atmosphere and average global temperatures rise, the frequency and intensity of powerful storm is increasing in northern Bangladesh and nearby Nepal, leading to more lightning strikes.

The LoGIC works with UPs and communities to develop strategies for adapting to the impacts of climate change, utilizing the Local Climate Adaptive Living Facility approach Rafinagar Union Parishad prioritise the building of a lightning shed with PBCRG support as a result of bottom-up consultations.

The sheds are constructed from concrete and stand some 10 metres high with a lightning rod on top that guides any strike safely into the earth. The sheds are accessible from the ground level via concrete steps during the dry season, when the hoar waters recede. Their two-storey design ensures that when the monsoon rains come and the wetlands return to a vast watery lake, boats can moor alongside the higher steps like a jetty, making it easy for passengers and fishermen to access the second-floor shelter. The structure has no walls, but it does have a roof to keep off the rain and a water pump to provide free fresh drinking water to anyone taking refuge. The sheds are also equipped with solar panels that power lights, so fishers and travellers can easily spot the shelters at night.

In the reporting year, the LoGIC project supported to construct three lightning sheds, which are now completed. The total cost of the investment is about USD 27,000 with co-finance of USD 480. Some 1,875 people are benefitting from the lightning sheds, 840 of which are women. The communities have set up an operation and maintenance committee to keep the lightning sheds operational.

Annex-1

Table of Contents

Abbreviation and Acronyms	2

Executive Summary	3

1.	Introduction and Background	4

1.1.	Objective of the study	4

1.2.	Key issues for evaluation	4

2.	Benefit-Cost of Climate Investment: Review of Literature	5

3.	Methodology and Approach	7

3.1.	Sample Size, Study Area, and Sampling Technique	7

3.2.	Analytical Technique for Impact Assessment	13

4.	Results: A quantitative Assessment (Based on FGD participants)	15

4.1.	Overall Scenario of Benefit-Cost Ratio (BCR) Analysis of the Study	15

4.2.	Climate Change Adaptation Category-Wise BCR Calculation	18

5.	A Qualitative Assessment (Based on FGD participants)	26

5.1.	Overall Benefit of Climate Change Adaptation Categories	26

5.2.	Climate Change Adaptation Categories	27

6.	KII participant’s perception on the performance assessment of the project	35

7.	Conclusion and Policy Recommendation	38

References	39

Annexes	40

# Abbreviation and Acronyms

| LOGIC | : | Local Government Initiative on Climate Change |
| --- | --- | --- |
| LGD | : | Local Government Division |
| UNDP | : | United Nation Development Program |
| UNCDF | : | United Nations Capital Development Fund |
| GoB | : | Government of Bangladesh |
| NGOs | : | Non-Government Organizations |
| EU | : | European Union |
| SIDA | : | Swedish International Development Agency |
| LGIs | : | Local Government Institutions |
| CSOs | : | Civil Society Organizations |
| CBA | : | Cost-Benefit Analysis |
| PBCRG | : | Performance Based Climate Resilient Grants |
| NPV | : | Net Present Value |
| IRR | : | Internal Rate of Return |
| MARR | : | Minimum attractive rate of return |
| BCR | : | Benefit Cost Ratio |
| SAM | : | Social Accounting Matrix |
| IOM | : | Input-output matrix |
| CGE | : | Computable general equilibrium |
| GDP | : | Gross Domestic Product |
| BAEC | : | Bangladesh Atomic Energy Commission |
| SLQ | : | Simple location quotients |
| APS | : | Average Propensities to Spend |
| DDLG | : | Deputy Director of Local Government |
| UNO | : | Upazila Nirbahi Officer |
| DCFC | : | District Climate Finance Coordinator |

# Executive Summary

The problems of climate change are now being discussed worldwide. Nowadays, these problems are more critical in developing or less developing countries like Bangladesh. To cope with these problems several climate change adaptation schemes or categories were implemented by the Local Government Division (LGD) in partnership with the United Nation Development Program (UNDP) and the United Nations Capital Development Fund (UNCDF) in vulnerable areas of Bangladesh. This study aims to evaluate the profitability analysis with the perception assessment of these climate change adaptation categories. In doing so, a multistage sampling technique was followed to conduct 84 focus group discussions (FGD) and 76 key informant interviews (KII). In the case of FGD, both quantitative (i.e., BCR) and qualitative (i.e., perception score index) analysis were used whereas KII only used qualitative analysis (i.e., perception score index and SWOT). The key findings of this study are as follows:

Quantitative analysis

- The estimated overall direct benefit and co-benefit are 62% and 38% respectively in terms of all implemented climate change adaptation categories;

- The calculated BCR is 3.91 for the total benefit consisting of direct (2.41) and co-benefit (1.50) in terms of the project;

- Adaptive water and sanitation solutions get the highest rank considering the total BCR among all adaptation categories and

- The highest percentage share is found for the category namely ‘reduce impacts of flood and waterlogging’ based on the direct benefit whereas based on the co-benefit, ‘adaptive water and sanitation solutions’ get the highest percentage share.

Qualitative analysis

- The study reveals social and environmental benefits as well;

- The estimated overall social benefit of the project is 81.51% indicating a very satisfactory level whereas a satisfactory level of benefit is found for overall environmental benefit;

- From KII, the study reveals a very satisfactory level for the overall performance of the project; and

- SWOT analysis reveals the strong backward and forward linkage as a strength, inefficient funding as a weakness, skill development programs as opportunities, and higher cost of supplies as a threat.

Based on the findings, the study recommends the implementation of more climate change adaptation plans so that residents of climate-vulnerable areas can easily maintain their way of life. The infrastructures must, however, be periodically monitored and, if necessary, maintained if they are to be used more widely and sustainably, given that they are located in relatively climate-vulnerable areas and regions.

# Introduction and Background

Bangladesh is one of the world's most disaster-prone countries where the impact of climate change exacerbates the governing factor of disasters. Given the current trends, it is anticipated to be the country most affected by climate change. The risk of a major hydro-meteorological disaster is also increasing. The country's geographical location makes it more vulnerable to frequent natural disasters such as floods, cyclones, earthquakes, etc. Flooding and cyclones are recurring phenomena that are likely to result in massive loss of life, property damage, and loss of livelihood (Islam, 2013). To cope with these climate-induced vulnerabilities, a project titled ‘Local Government Initiative on Climate Change (LoGIC)’ was implemented by the Local Government Division (LGD) in partnership with UNDP and UNCDF (i.e. technical and management support) which was funded by the multi-donor collaborative initiative of GoB, UNDP, UNCDF, EU, and government of Sweden. The Project provided US$ 7.91 million as additional funding to 72 union Parishads through government-to-local fiscal transfer channels. This funding is earmarked to fill gaps in existing union Parishad plan financing for the public service and infrastructure priorities identified in the Risk Reduction Action Plan, i.e., ensuring that local infrastructures meet climate change-related national technical standards. The project is designed to enhance the capacity of vulnerable communities, Local Government Institutions (LGIs), and Civil Society Organizations (CSOs) for planning and financing climate change adaptation solutions in selected climate-vulnerable areas. This study aims to assess the impacts of climate change adaptation measures among vulnerable people throughout the prominent areas of Bangladesh.

# Objective of the study

Overall, the project is expected to raise perceptions on the importance of adapting climate change-related strategies by analyzing the project implementation costs and benefits. The specific objective is as follows:

- To evaluate the profitability analysis of climate change adaptation measures/and categories and

- To assess the perception on climate change adaptation category and/or measures

# Key issues for evaluation

LoGIC PBCRG has been invested in a wide range of potential investments in the following key intervention areas in seven districts, each with its own set of socioeconomic, environmental, and climate-related challenges. The following key investment areas  are provided below:

- Climate-resilient safe water and sanitation solutions;

- Promotion of climate-adaptive and environment-friendly irrigation systems and agricultural practices (canal re-excavation, solar-powered irrigation system, etc.);

- Nature-based solutions (including plantations and plant nurseries);

- Improving WASH and other facilities in cyclone and flood shelters in climate-vulnerable areas with a special focus on women’s needs;

- Improving access to cyclone shelters, flood shelters, and kellas in climate-vulnerable areas (Roads and bridges);

- Reduce the impacts of climate change-induced floods and waterlogging (e.g., culvert, drain, flood protection walls, guide walls, and roads);

- Improving absorptive, adaptive, and transformative capacity

- Enhance the safety of vulnerable people from climate change-related extreme weather events (providing safety equipment to sea-going fishing boats and lightening/flood shelter).

# Benefit-Cost of Climate Investment: Review of Literature

Arfanuzzaman et al. (2021) conducted an extended cost-benefit analysis in the lower Teesta basin (LTB) of Bangladesh. According to the study, shallow tube-well (STW) irrigation practices in both sandy and loamy soil have the highest marginal adaptation cost (MAC) but the lowest benefit-cost ratio (BCR). Due to the high cost of the government's initial establishment, deep tube-well (DTW) irrigation generates superior benefits for farmers compared to STW irrigation. Though the MAC for short-duration variety (SDV) rice is relatively low among the promising adaptations, its economic profitability is 62 percent lower than that of maize cultivation. However, maize cultivation generates US$86 more welfare to farmers than SDV rice, which may strengthen farmers' preference for maize cultivation over SDV rice. Strategic adaptation planning, soft credit, technological advancement, and subsidized agricultural inputs will encourage farmers to implement adaptation options that may reduce climate-induced loss and damages for farmers and build socioeconomic resilience in other similar areas of South Asia.

Williams et al. (2020) undertook a cost-benefit analysis (CBA) of adopting climate adaptation practices among Ghanaian smallholders. In two horticultural crop-growing municipalities, 180 smallholder households that had implemented the identified practices were surveyed. Profitability indicators, as well as an assessment of environmental and social externalities, were used to estimate the cost-effectiveness of the practices. The findings indicated that implementing any of the five adaptation practices would yield positive results from both the private and public sectors. However, given the capital required, the payback period for investments made, and the risks associated with implementation, two of the five practices are particularly suitable for smallholders. If all of the Institutional and policy support is required if all of the practices are to be implemented proposes integrating localized climate vulnerability and economic assessments for enhanced climate adaptation actions to broaden information on the potential of climate adaptation.

Akinola et al. (2019) conducted a study on the potential economic impacts of climate adaptation research in Nigeria. As a result, Nigeria's Baseline Study was launched in order to serve as a reference point for targeted agricultural investments. Stress-resistant varieties, improved management techniques, and irrigation techniques are likely the research options for maize and rice. This study documented empirical research on the returns to climate change adaptation strategies using a combination of primary data from a survey of 3600 crop farming households and secondary data from the FAO database. In the case of maize, improved management techniques had the lowest internal rates of return (IRR) (32%), while stress-resistant varieties had the highest (84%). Irrigation methods had the highest cost-benefit ratio of 12.4. The estimated number of people who benefited from the technologies ranges from 23 million to 36 million. Economic indicators for Rice follow the same pattern. The values, however, are lower. Changes in adoption rate are more responsive to the technologies than changes in costs. The potential economic gains are substantial. However, effective dissemination strategies are required because the realization of these gains is dependent on deployment and dissemination approaches.

Mtimuni and Campus (2018) pursued to identify the various adaptation strategies, factors influencing adaptation choice, and the costs and benefits of the most cost-effective identified adaptation strategy. Under World Vision, the study was carried out in the Chitethekwere, Nkhoma, and Lilongwe districts. To model, the relationships between the polytomous response variables and a set of variables, a multinomial logit model (MNL) was used. According to the study's findings, six of the seven discovered adaptation strategies were cost-effective, with an NPV greater than one. The traditional adaptation strategy (katutu) was not profitable because its NPV was less than one, indicating that the overall benefit accrued was less than the cost. According to the findings of the study, conservation agriculture had the greatest impact.

Devkota et al. (2017) estimated the cost and benefit of rural rice farmers in Nepal adopting climate change adaptation options. The study followed a multi-stage sampling technique and then collected data from 773 households using a structured questionnaire. In doing so, the study covered seven districts, three in the Terai and four in the Hilly region of Nepal. The study revealed that rice farmers use 13 major adaptation strategies to protect themselves from climatic risk.  The first three most expensive adaptation options are alternative irrigation practices, which cost an average of US $ 69.95 (US$ 1 = 102.84 Nepalese Rupees), denser plantation of local seeds ($ 20.69), and using climate-smart varieties ($ 18.06). Almost 88 percent of farmers used more than one adaptation strategy on the same farm to reduce the impact of extreme climatic conditions. Total cost and revenue revealed that the total cost per unit ranges from $ 28.34 to $ 32.79, while the total revenue per unit ranges from $ 33.4 to $ 49.02. Surprisingly, farmers who do not use any adaptation strategies are able to earn the highest per unit production income.

Shongwe et al. (2013) carried out a study to identify private adaptation strategies to climate change, as well as a cost-benefit analysis of the identified adaptation strategies in Lowveld of Swaziland. To select 350 households, a stratified random sampling technique was used, and all households were interviewed directly using a structured questionnaire. The data were analyzed using descriptive statistics and cost-benefit analysis, with net present value (NPV) and internal rate of return (IRR) serving as decision rules. Drought-resistant varieties, crop rotation, mulching, minimum tillage, early planting, late planting, and intercropping were all used as adaptation strategies. Switching crops had the highest NPV, with maize (E14.40) being replaced by drought-tolerant crops such as cotton (E1864.40), sorghum (E283.30), and dry beans (E292.20). Instead of maize, the study suggests that households grow drought-tolerant crops such as cotton, sorghum, and dry beans. In order to improve crop production, the government should build irrigation infrastructure such as dams, strengthen extension services, and subsidize farm inputs.

Kalame et al. (2011) conducted research on a win-win practice for forestry and climate change adaptation in the case of a modified taungya system (MTS) in Ghana. The findings show that MTS considers the majority of adaptation strategy activities, is a profitable venture (BCR > 1), and has a high potential to reduce vulnerability due to short-term food production and long-term plantation establishment. In the short term, resource management in MTS appears promising, but challenges remain in meeting livelihood and adaptation needs in the medium and long term. We conclude that MTS has the potential to be a win-win practice in terms of forestry and adaptation. The legalization of all contractual agreements, combined with ongoing monitoring, evaluation, and improvement, may propel MTS to become a long-term activity.

# Methodology and Approach

# Sample Size, Study Area, and Sampling Technique

Review of the Annual Progress Review (APR) and Mid-Term Evaluation (MTE) approaches envisaged that it is challenging to consider all climate change adaptation categories and or measures for impact evaluation implemented by LoGIC. The Annual Progress Review (APR), 2021 focused on agriculture and irrigation, water supply, health and sanitation, and adaptive infrastructure schemes by addressing awareness, plantation, solar-powered irrigation systems, sanitation, salinity, flood-resistant tube well for drinking water, river erosion, floods, tidal surges, dams, roads, smart boats, bridges, and culverts as climate change adaptation strategies. Furthermore, the socioeconomic characteristics covering 320 sample size were analyzed through the direct interview method from four locations – flashflood-prone haor area (Sunamganj), flood-prone char area (Kurigram), south-west coastal area (Bagerhat), and south-central area (Barguna). On the other hand, agriculture and innovation, water supply, health and sanitation, adaptive infrastructure, plantation, fisheries, and other schemes were focused by emphasizing solar power irrigation, rainwater harvesting structures, integrated drinking water plants, toilet, drainage, culvert, emergency center, guide walls, tree plantation, and smart boat as climate change adaptation strategies in the Mid-Term Evaluation (MTE), 2022. KIIs with Deputy Director of Local Government (DDLGs), Upazila Nirbahi Officers (UNOs), Union Parishad (UP) Chairmen, FGDs, and PRAs with beneficiaries were conducted in 19 Upazila MTE-2022. No household surveys were conducted in MTE, 2022.

In this impact evaluation, we conducted a Benefit Cost Ratio (BCR) analysis based on the climate change adaptation category and climate change adaptation measures. In doing so, following the approval of the UNCDF officials, twenty-nine (29) climate change adaptation measures were selected from eight (8) climate change adaptation categories (out of 11 categories) based on the prominence and the amount of PBCRG investment of the LoGIC project (see Column A and B in Table 1). Thus, we selected five hundred and seventy-eight (578) schemes (out of 645) under twenty-nine (29) climate change adaptation measures. Later, by using a standard formula for determining sample size for finite populations supported by Singh and Masuku (2014), we found eighty-one (81) schemes among 578. The following formula (I) was applied at a 95% confidence level by considering a 10% margin of error. Here, we considered a 10% margin of error instead of ≤5% due to the small size finite population.

If we assume ≤5%, the calculated sample size will be large and vice-versa (Singh and Masuku, 2014). The equation is given below:

SS

Where,

SS=Sample size, z-score=1.96, p=0.50, e=0.10 and N=578.

Based on this calculated number of selected schemes, we used weight to see the distribution for each of the climate change adaptation measures (see Column D in Table 1). The weighted values which were smaller than 1, have been considered as 1. For instance, 3 weighted values for 3 climate change adaptation measures (water desalination plant, hydroponics, and swamp plantation) were considered as 1. Thus we get 84 (81+3) schemes for all the climate change adaptation measures (see Column D in Table 1) which is showing only the number of schemes but does not represent the specific study areas i.e., the name of the areas in which the schemes were implemented. Therefore, the number of weighted values of each climate change adaptation measure was used as a top scheme (based on investment and prominence) in order to identify the study areas where these were implemented. In such a way, we designated 44 unions, 18 Upazilas, and 7 districts (see Columns E, F, and G in Table 1). The technique of sampling is presented in Figure 1.

Table 1. Distribution of sample based on categories and sub-categories

| A | B | C | D | E | F | G | *H |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Climate change adaptation categories | Climate change adaptation measures | **Total scheme | Selected schemes | District | Upazila | Union | FGD |
| Adaptive Water and Sanitation Solutions | Rainwater Harvesting System (Community Level) | 70 | 10 | Khulna | Koyra | Moheshwaripur, Maharajpur, Koyra, Uttar Bedkashi, Dakkhin Bedkashi | 10 |
|  |  |  |  | Bagerhat | Mongla | Chandpai |  |
|  |  |  |  |  | Sarankhola | Rayenda |  |
|  | Combined Rainwater Harvesting and Pond water Treatment Plan | 24 | 3 | Bagerhat | Morelganj | Nishanbaria | 3 |
|  |  |  |  |  | Mongla | Sundarban |
|  |  |  |  |  | Sarankhola | Khontakata |
|  | Flood Proof Tube-well | 38 | 5 | Kurigram | Chilmari | Raniganj, Ashtamirchar | 5 |
|  |  |  |  |  | Rowmari | Rowmari |  |
|  |  |  |  |  | Char Rajibpur | Rajibpur |  |
|  |  |  |  | Sunamganj | Derai | Charnarchar |
|  | Solar Powered Ground Water Treatment Plan | 8 | 1 | Kurigram | Rowmari | Bondober | 1 |
|  | Pond Water Treatment Plant | 5 | 1 | Bagerhat | Morelganj | Nishanbaria | 1 |
|  | Improve WASH Facility in Flood Shelter | 15 | 2 | Kurigram | Char Rajibpur | Rajibpur | 2 |
|  |  |  |  |  | Rowmari | Rowmari |  |
|  | Solar Powered Pond Water Treatment Plant | 15 | 2 | Khulna | Dacope | Sutarkhali | 2 |
|  | Water Desalination Plant (Reverse Osmosis) | 3 | 1 | Khulna | Koyra | Koyra | 1 |
| Reduce Loss and Damage of Life and Property | Provide Safety Equipment to Fishing Boats | 31 | 4 | Bhola | Bhola Sadar | Rajapur | 4 |
|  |  |  |  |  | Borhanuddin | Bara Manika |
|  | Lightening Shed | 8 | 1 | Sunamganj | Derai | Rafinagar | 1 |
|  | Provide Safety Equipment to Passenger Boats, Provide Safety Equipment to Fishing Boats | 18 | 3 | Sunamganj | Shalla | Habibpur, Atgaon | 3 |
|  |  |  |  |  | Tahirpur | Dakkhin Baradal |
| Reduce Impacts of Flood and Waterlogging | Culvert | 69 | 10 | Barguna | Barguna Sadar | Dhalua, Naltona, Badarkhali | 10 |
|  |  |  |  | Bhola | Bhola Sadar | Rajapur, Dakkhin Digholdi |
|  |  |  |  | Kurigram | Char Rajibpur | Mohanganj |
|  |  |  |  |  | Chilmari | Thanahat |  |
|  |  |  |  | Bagerhat | Sarankhola | Rayenda |  |
|  |  |  |  | Sunamganj | Tahirpur | Uttar Sreepur |
|  | Drain | 26 | 4 | Bhola | Daulatkhan | Uttar Joynagar, Sayedpur | 4 |
|  |  |  |  |  | Bhola Sadar | Dhania, Dakkhin Digholdi |
|  | Drain and Culvert | 4 | 1 | Bhola | Bhola Sadar | Dhania |
|  | Village Protection Wall | 16 | 2 | Sunamganj | Derai | Charnarchar | 2 |
|  |  |  |  |  | Tahirpur | Dakkhin Baradal |
|  | Guide Wall | 15 | 2 | Bagerhat | Mongla | Sundarban | 2 |
|  |  |  |  | Kurigram | Rowmari | Bondober |
|  | Flood Protection Wall | 9 | 1 | Patuakhali | Rangabali | Char Montaaj | 1 |
| Improve Accessibility Flood Shelter, Cyclone Shelter, Kella and Water Source | Road Construction/Repair/ | 78 | 11 | Khulna | Koyra | Moheshwaripur, Uttar Bedkashi,Koyra, Maharajpur | 11 |
|  |  |  |  |  | Dacope | Tildanga, Kamarkhola, Sutarkhali |
|  |  |  |  | Bhola | Bhola Sadar | Rajapur |  |
|  |  |  |  |  | Daulatkhan | Char Khalifa |
|  | Bridge | 11 | 2 | Bagerhat | Morelganj | Baraikhali | 2 |
| Promote Climate Resilient Agriculture | Canal Re-excavation | 17 | 2 | Barguna | Barguna Sadar | Badarkhali | 2 |
|  |  |  |  |  | Taltoli | Barabagi |  |
|  | Agricultural Demonstration | 12 | 2 | Bhola | Daulatkhan | Uttar Joynagar | 2 |
|  |  |  |  |  | Borhanuddin | Bara Manika |
|  | Solar Powered Surface Water Irrigation | 22 | 3 | Bhola | Daulatkhan | Uttar Joynagar | 3 |
|  |  |  |  |  | Bhola Sadar | Rajapur |  |
|  |  |  |  | Bagerhat | Sarankhola | Rayenda |  |
|  | Solar Powered Ground Water Irrigation | 21 | 3 | Bagerhat | Sarankhola | Khontakata | 3 |
|  |  |  |  | Kurigram | Rowmari | Rowmari |  |
| Improve Adaptive, Absorptive and Anticipatory Capacity | Shuhashni Sales Center | 13 | 2 | Sunamganj | Tahirpur | Uttar Sreepur | 2 |
|  |  |  |  | Barguna | Pathorghata | Nachnapara |
|  | Solar Panel Distribution (at Household Level) | 5 | 1 | Kurigram | Chilmari | Ashtamirchar | 1 |
|  | Awareness Raising Billboard | 12 | 2 | Sunamganj | Shalla | Atgaon | 2 |
|  |  |  |  |  | Derai | Bhatipara |  |
|  | Provide instrument support to PCSBA and Community Clinics | 9 | 1 | Sunamganj | Shalla | Bahara | 1 |
| Nature-based Solutions | Swamp Plantation | 2 | 1 | Sunamganj | Tahirpur | Dakkhin Sreepur | 1 |
| Climate Resilient Livestock Solution | Hydroponics | 2 | 1 | Bagerhat | Morelganj | Jiudhara | 1 |
| Total |  | 578 | 84 |  |  |  | 84 |
| Note: *H shows the number of FGD which is equal to the number of schemes; **Total scheme calculated based on climate change adaptation measures |

For the costing exercise, two types of data are needed – costs (i.e. investment and maintenance) and benefits.

Cost (Investment) data, has two sources. One is PBCRG investment and the other is co-finance investment (co-finance means the finance received from other sources/institutions/organizations) for each of the climate change adaptation measures provided by the project. The cost data were compiled according to the identified climate change adaptation measures which were verified by the LoGIC project team.

Benefits and avoided cost/co-benefits data were collected through focus group discussion (FGD) with the local communities (such as crop farmers, poultry/livestock farmers, fish farmers/ fishermen, day laborers, small businessmen, salaried job holders, housewives, and so on). The number of FGD is equal to the number of selected schemes (see Column H Table 1). About 10 to 13 beneficiaries were included in each FGD. In addition, LoGIC's field team members provided the necessary information and guidance (e.g., identification of scheme, key people, locations, etc.) to facilitate the FGDs. The FGD was conducted using a well-structured questionnaire through a direct discussion with the beneficiaries. Before, starting FGD the note-takers (enumerators) delivered a short brief to the participants about the LoGIC project. They sought the participant’s feedback (i.e., benefits) based on the schemes implemented by the LoGIC project. Thus the study differentiated the LoGIC benefits from other’s interventions.

Finally, Key Informant Interviews (KIIs) were performed to identify the benefits, along with evaluating the project’s performance. Besides, the study assessed the strength, weaknesses, opportunities, and threats of the project by KIIs. Since we selected 44 unions from 18 Upazilas under 7 districts, we carried out seventy-six (76) KIIs which consists of 44 union chairmen, 18 Upazila Nirbahi Officers (UNOs), 7 District Climate Finance Coordinator (DCFCs), and 7 Deputy Director of Local Government (DDLGs) in where the respective sub-categories were implemented.

# Analytical Technique for Impact Assessment

The study followed two types of impact assessment. The first one is quantitative impact assessment and the other one is qualitative impact assessment. In the case of the quantitative approach, the study used financial assessment methods to examine the LoGIC interventions. Besides, the perception index method was used in the case of qualitative impact assessment.

In line with the well-accepted practices, the study applied the Benefit-Cost Ratio (BCR) in the case of the financial assessment. Investors use these quantitative measures to help them decide whether to undertake investment or not, based on their return requirements. The benefit-cost method is often used for public projects. The method compares project benefits to the cost of the project, and for the project to be viable, the benefits have to be greater than the cost. By definition, project benefits are the favorable consequences of the project to the public, and project cost is the monetary disbursement required of the government (Sullivan et al., 2006).

Park (2002) describes benefit-cost analysis as “a decision-making tool used to systematically develop useful information about the desirable and undesirable effects of public projects”. He defines three types of benefit-cost analysis problems:

- Maximizing the benefits for any given set of costs

- Maximizing the net benefits when both benefits and costs vary;

- Minimizing cost to achieve any given level of benefits.

The worthiness of a public project can be expressed by comparing the benefits (B) of the project to the investment/cost (C) of the project by taking the ratio B/C, i.e. the Benefit-Cost ratio (BCR). The ratio is calculated as:

=

Furthermore, a qualitative impact assessment was performed for the indicators (benefit and co-benefit items) which were not measurable in monetary form. In such case, the study developed the extent of participants’ perception in the case of benefit and co-benefit by following the five (5) points of the Likert scale (Very much=5, Much=4, Neutral=3, Less=2, Very less=1) technique (Likert, 1932). The perception extent of the beneficiary and stakeholder was measured by the following formula:

Based on the index score, the study ranged the values by adopting the study of Polemi (2018). Values that were lies ≥80% of any climate change adaptation action were considered to be in very good (satisfactory) condition. The climate change adaptation action was considered as good (satisfactory) if the index values lie between ≥60% and <80%, medium (neutral) if index values were ≥40% and <60%, less satisfaction if were between ≥20% and <40%, and very less satisfaction if the values were between 1% to <20%.

Finally, the study performed a SWOT (Strengths, Weaknesses, Opportunities, and Threats) analysis to see the project’s status.

# Results: A quantitative Assessment (Based on FGD participants)

# Overall Scenario of Benefit-Cost Ratio (BCR) Analysis of the Study

Investment/cost scenario

According to the Terms of Reference (ToR) and UNCDF sources, it is evident that about BDT 553 million (consisting of BDT 460 million from PBCRG investment/cost, and 93 million from other sources (i.e., co-finance)) was injected into the most vulnerable communities throughout the seven districts of Bangladesh to cope with climate change adaptation. However, a total of BDT 131.58 million (i.e., 24%) consists of BDT 97.92 million (74.42%) from PBCRG and BDT 33.66 million (25.58%) from other sources have taken into account as cost/investment to assess BCR in this study (Figure 2).

Figure 2. Percentage distribution of PBCRG and Co-finance investment

The estimated cost (%) was then distributed among the adaptation category to see the highest contribution (i.e., higher rank) in the case of mitigating climate impacts among the vulnerable communities which are presented in Table 2. Considering the total investment (%), the study found a higher rank for the category of ‘adaptation water and sanitation solution’ among all. The highest grant was provided to implement this climate change adaptation category because the most climate-vulnerable people particularly in Khulna, Bagerhat, Sunamganj, and Kurigram face this issue mostly during different types of natural hazards such flush floods, cyclones, and so on.

Table 2. Investment distribution among the selected climate change adaptation category (in %)

| Climate change adaptation category | PBCRG Investment (%) | Rank of PBCRG investment | Co-finance Investment (%) | Rank of co-finance investment | Total Investment (%) | Rank of total investment |
| --- | --- | --- | --- | --- | --- | --- |
| Adaptive Water and Sanitation Solutions | 29.26 | I | 2.44 | IV | 31.70 | I |
| Reduce Loss and Damage of Life and Property | 4.87 | V | 17.22 | I | 22.09 | II |
| Reduce Impacts of Flood and Waterlogging | 14.60 | II | 2.92 | II | 17.52 | III |
| Improve Accessibility to Flood Shelter, Cyclone Shelter, Kella, and Water Source | 11.81 | III | 0.48 | V | 12.30 | IV |
| Promote Climate Resilient Agriculture | 9.54 | IV | 2.45 | III | 11.99 | V |
| Improve Adaptive, Absorptive, and Anticipatory Capacity | 3.18 | VI | 0.06 | VI | 3.24 | VI |
| Nature-based Solutions | 0.76 | VII | 0.02 | VII | 0.78 | VII |
| Climate Resilient Livestock Solution | 0.39 | VIII | 0.00 | VIII | 0.39 | VIII |
| Total | 74.42 |  | 25.58 |  | 100 |  |

Note: The percentages (%) were calculated based on the total investment incurred for the selected category of schemes, and a higher percentage indicates a higher rank.

Overall benefit-cost (BCR) scenario

It is promising that the implemented project provided direct benefits (the main purpose of implementation) and co-benefit (indirect benefit or additional benefit) among the vulnerable communities. The study finds 62% direct benefit and 38% co-benefit (i.e. Figure) 3. Considering the direct benefit and the co-benefit, estimated both of the BCRs are greater than 1. Besides, as the overall BCR of the project is greater than 1, therefore the project delivers a positive net present value to a firm and its investors (Table 3).

Figure 3. Percentage distribution of direct benefit and co-benefit

Table 3. Overall benefit-cost ratio (BCR) of the study

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 96.02 |
| Co-finance investment (Tk. in million) | 33.64 |
| Total investment (Tk. in million) | 129.66 |
| Direct benefit (Tk. in million) | 312.29 |
| Co-benefit (Tk. in million) | 195.11 |
| Total benefit (Tk. in million) | 507.40 |
| BCR based on direct benefit | 2.41 |
| BCR based on co-benefit | 1.50 |
| BCR based on total benefit | 3.91 |

Note: Investment in swamp plantations and billboards has not been considered to estimate BCR since the financial benefit has not been explored for both cases.

Ranks of the climate change adaptation categories based on benefits

From Table 4, it is noted that the BCR is higher for ‘adaptive water and sanitation solution’ and therefore it attaches higher rank considering the total benefit. Although, this scheme scores a higher rank while considering the total co-benefit while it scores 3rd rank in the case of direct benefit. This means that vulnerable people enjoy more additional benefits than direct benefits from the scheme. Surprisingly, improving accessibility to flood and cyclone shelter scores 2nd and 1st rank in the case of total and direct benefit respectively, though a lower investment was provided to it as discussed earlier in Table 2. This means the community people enjoy many more direct benefits such as easy access to flood and cyclone shelters during emergency cases due to the establishment of bridges and construction of roads.

Table 4. Ranks of the climate change adaptation category

| Climate change adaptation category | BCR |
| --- | --- |
|  | Direct benefit | Rank (Direct benefit) | Co-Benefit | Rank (Co-Benefit) | Total benefit | Rank (Total benefit) |
| Adaptive water and sanitation solutions | 2.41 | III | 3.19 | I | 5.60 | I |
| Reduce loss and damage of life and property | 1.58 | V | 1.16 | III | 2.74 | V |
| Reduce impacts of flood and waterlogging | 3.25 | II | 0.17 | VII | 3.42 | III |
| Improve accessibility to flood shelter, cyclone shelter, kella, and water source | 3.82 | I | 0.25 | VI | 4.07 | II |
| Promote climate-resilient agriculture | 1.41 | VI | 0.99 | V | 2.40 | VII |
| Improve adaptive, absorptive, and anticipatory capacity | 1.82 | IV | 1.13 | IV | 2.96 | IV |
| Nature-based solutions* | - | - | - | - | - | - |
| Climate resilient livestock solution | 1.16 | VII | 1.36 | II | 2.52 | VI |

Note: * Indicates the financial benefit has not been identified therefore the study did not calculate BCR on it.

Distribution of direct and co-benefit

The distribution of direct and co-benefit of each of the climate change adaptation categories are presented in Table 5. The study finds higher co-benefit than the benefit for adaptive water and sanitation solutions and climate resilient livestock solutions. The people who quested pure drinking water can save time now due to the implementation of water and sanitation scheme which helps to increase their income through involvement in income-generating activities. On the other hand, due to the adaptation of climate-resilient livestock solutions the availability of feed such as grass increases which reduces their feed cost.

Table 5. Percentage distribution of direct and co-benefit

| Climate change adaptation category | BCR | Share (%) |
| --- | --- | --- |
|  | Direct benefit | Co-Benefit | Total benefit | Direct benefit (%) | Co-Benefit (%) |
| Adaptive water and sanitation solutions | 2.41 | 3.19 | 5.6 | 43.04 | 56.96 |
| Reduce loss and damage of life and property | 1.58 | 1.16 | 2.74 | 57.66 | 42.34 |
| Reduce impacts of flood and waterlogging | 3.25 | 0.17 | 3.42 | 95.03 | 4.97 |
| Improve accessibility to flood shelter, cyclone shelter, kella, and water source | 3.82 | 0.25 | 4.07 | 93.86 | 6.14 |
| Promote climate-resilient agriculture | 1.41 | 0.99 | 2.4 | 58.75 | 41.25 |
| Improve adaptive, absorptive, and anticipatory capacity | 1.82 | 1.13 | 2.96 | 61.49 | 38.18 |
| Nature-based solutions* | - | - | - | - | - |
| Climate resilient livestock solution | 1.16 | 1.36 | 2.52 | 46.03 | 53.97 |

# Climate Change Adaptation Category-Wise BCR Calculation

Adaptive water and sanitation solutions

It is reported that the project provides different climate change adaptation actions such as the rainwater harvesting system, combined rainwater harvesting, and pond water treatment plan, flood-proof tube-well, solar powered groundwater treatment plan, pond water treatment plant, improve wash facility in flood shelter, solar powered pond water treatment plant, and water desalination plant (reverse osmosis) which implemented as adaptive water and sanitation solutions for the climate vulnerable people. However, from Table 6, it is evident that the cumulative BCR is 5.60 consisting of 2.41 for direct benefit and 3.19 for co-benefit indicating a tremendous positive implication of investment in the project areas. This remarkable output has been possible due to the generating direct benefit and co-benefit as well (see BOX 2). The community people are now completely able to reduce expenditure on searching for pure water and it also reduces the health cost than before. On the other hand, due to the establishment of climate change adaptation measures, the people of the community can increase their income as a result of saving time.

Table 6. Adaptive water and sanitation solutions

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 38.51 |
| Co-finance investment (Tk. in million) | 3.21 |
| Total investment (Tk. in million) | 41.72 |
| Direct benefit (Tk. in million) | 100.52 |
| Co-benefit (Tk. in million) | 133.22 |
| Total benefit (Tk. in million) | 233.75 |
| BCR based on direct benefit | 2.41 |
| BCR based on co-benefit | 3.19 |
| BCR based on total benefit | 5.60 |

Reduce loss and damage of life and property

Reducing loss and damage of life and property is another scheme that covers the climate change adaptation measures such as safety equipment for fishing boats, lightening sheds, and safety equipment for passenger and fishing boats. The result presented in Table 7. shows a positive BCR indicating that the community people are benefiting directly or indirectly from the actions. Due to getting safety equipment like a life jacket, smart boat, etc. now fishermen can catch fish safely for a longer duration, and thus their income is increased to the pre-intervention period (see in BOX 3). In addition, some of the people earned money during the construction period of the lightening shed. The community people use this shed to protect themselves from the lightning. Not only that but also, the poor people who rear cattle, goats, sheep, etc. in the open field can save their livestock using this shed during bad weather. Now, this shed is also used as a shelter center during the flush flood.

Table 7. Reduce loss and damage of life and property

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 6.41 |
| Co-finance investment (Tk. in million) | 22.66 |
| Total investment (Tk. in million) | 29.07 |
| Direct benefit (Tk. in million) | 45.95 |
| Co-benefit (Tk. in million) | 33.82 |
| Total benefit (Tk. in million) | 79.77 |
| BCR based on direct benefit | 1.58 |
| BCR based on co-benefit | 1.16 |
| BCR based on total benefit | 2.74 |

Reduce impacts of flood and waterlogging

It is evident that to reduce the impacts of flood and waterlogging, the project implemented culvert, drain, village protection walls, guide wall, and flood protection wall as climate change adaptation measures. From Table 8, the study finds an overall BCR which is 3.42 including the BCR of total direct benefit (3.25) and total co-benefit (0.17) indicating the satisfactory level of the measures taken. The taken climate change adaptation measures are beneficial to vulnerable peoples, particularly crop farmers and fish farmers. For instance, on the one hand, as crops are protected from damage, crop production is also increasing due to the implementation of these which accelerated the income of the farmers (see BOX 4). Besides, the fish farmers are benefited by protecting their ponds from flooding.

Table 8. Reduce impacts of flood and waterlogging

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 19.21 |
| Co-finance investment (Tk. in million) | 3.84 |
| Total investment (Tk. in million) | 23.05 |
| Direct benefit (Tk. in million) | 74.96 |
| Co-benefit (Tk. in million) | 3.95 |
| Total benefit (Tk. in million) | 78.91 |
| BCR based on direct benefit | 3.25 |
| BCR based on co-benefit | 0.17 |
| BCR based on total benefit | 3.42 |

Improve accessibility to flood shelter, cyclone shelter, kella, and water source

The two climate change adaptation measures such as bridge and road construction both are implemented such as citizens can move to flood and cyclone shelters easily when needed. Another aim of this intervention is to prevent waterlogging during floods and cyclones. However, the study finds the positive impacts as identified BCR is greater than 1 (Table 9). The common people especially crop farmers, fish farmers, and day laborers have benefited a lot financially from its establishment. Apart from the ease of communication, the cost of transportation for the general public has also been reduced to a great extent (see Box 5).

Table 9. Improve accessibility to flood shelter, cyclone shelter, kella, and water source

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 15.55 |
| Co-finance investment (Tk. in million) | 0.64 |
| Total investment (Tk. in million) | 16.18 |
| Direct benefit (Tk. in million) | 61.86 |
| Co-benefit (Tk. in million) | 4.05 |
| Total benefit (Tk. in million) | 65.91 |
| BCR based on direct benefit | 3.82 |
| BCR based on co-benefit | 0.25 |
| BCR based on total benefit | 4.07 |

Promote climate-resilient agriculture

The project has taken action to promote climate-resilient agriculture through the implementation of canal re-excavation, agricultural demonstration, solar-powered groundwater irrigation, and solar-powered surface water irrigation in vulnerable climate-prone areas. The results in Table 10 show positive BCR which means the monetary value for the identified benefits outweighs the cost (investment) of this study. Income increase from crops, fishing, wage, and pond aquaculture and expenditure reduction on fuel/diesel for irrigation has been reduced remarkably which is reported by the beneficiaries (see BOX 6).

Table 10. Promote climate resilient agriculture

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 12.56 |
| Co-finance investment (Tk. in million) | 3.22 |
| Total investment (Tk. in million) | 15.77 |
| Direct benefit (Tk. in million) | 22.27 |
| Co-benefit (Tk. in million) | 15.56 |
| Total benefit (Tk. in million) | 37.83 |
| BCR based on direct benefit | 1.41 |
| BCR based on co-benefit | 0.99 |
| BCR based on total benefit | 2.40 |

Improve adaptive, absorptive, and anticipatory capacity

Improve adaptive, absorptive, and anticipatory capacity covers the climate change adaptation measures such as Shuhashni Sales centers, solar panel distribution, awareness-raising billboards, and providing instrument support to PCSBA and community clinics. Table 11 presents favorable BCR in the case of direct benefit (1.82), co-benefit (1.13), and total benefit (2.96). This is because of the extraction of direct and co-benefits (see BOX 7) from the climate change adaptation measures. According to the field observation, the people particularly the farmers are now able to increase their income by selling higher quantities of agricultural products easily in the Shuhasini sales center. In addition, a decrease in expenditure for fuel/diesel/kerosene, increase their savings due to the solar panel installation at the household level. Not only that but also, the other income-generating activities (IGAs) like handicrafts are performed by the women of the household due to getting time at night.

Table 11. Improve adaptive, absorptive, and anticipatory capacity

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 3.28 |
| Co-finance investment (Tk. in million) | 0.08 |
| Total investment (Tk. in million) | 3.36 |
| Direct benefit (Tk. in million) | 6.13 |
| Co-benefit (Tk. in million) | 3.81 |
| Total benefit (Tk. in million) | 9.94 |
| BCR based on direct benefit | 1.82 |
| BCR based on co-benefit | 1.13 |
| BCR based on total benefit | 2.96 |

Climate resilient livestock solution

Another climate change adaptation category is climate resilient livestock solution, which consists of a climate change adaptation measure, hydroponics, implemented for climate-vulnerable people in the Bagerhat district. Table 12 presents that the cumulative BCR is 2.52, with 1.16 for direct benefit and 1.36 for co-benefit, indicating a positive and satisfactory implication of project investment. This was made possible by receiving both direct and co-benefits (see BOX 8). For example, an increase in income for livestock farmers on the one hand, and a decrease in feed costs on the other, are identified as direct and co-benefits in this study.

Table 12. Climate resilient livestock solution

| Items | Value |
| --- | --- |
| PBCRG investment (Tk. in million) | 0.52 |
| Co-finance investment (Tk. in million) | 0.00 |
| Total investment (Tk. in million) | 0.52 |
| Direct benefit (Tk. in million) | 0.60 |
| Co-benefit (Tk. in million) | 0.70 |
| Total benefit (Tk. in million) | 1.30 |
| BCR based on direct benefit | 1.16 |
| BCR based on co-benefit | 1.36 |
| BCR based on total benefit | 2.52 |

# A Qualitative Assessment (Based on FGD participants)

The study also evaluates a qualitative analysis along with the quantitative one. For qualitative assessment, the study has taken responses from the participants based on the 5-point of Likert scale which is a worldwide familiar and acceptable method (Likert, 1932). After indexing, the study ranges the values to define the scenario of the project based on Polemi (2018) which is presented in BOX 9.

# Overall Benefit of Climate Change Adaptation Categories

The study reports the overall direct and indirect (co-benefit) benefits from the social and environmental aspects which are presented in Figure 4. The estimated perception score is 84% (lies between the points of 80% to 100%) for direct social benefit indicating a very satisfactory level of benefit extracted from the implemented climate change adaptation categories. Also, indirect social benefit (79%) implies a satisfactory level of the climate change adaptation categories. On the other hand, direct and indirect environmental benefits both are lies between 60% to 80% which indicates a pleasant level of benefits that are provided by the implemented adaptation categories.

Figure 4. Overall benefit of climate change adaptation categories

# Climate Change Adaptation Categories

Adaptive water and sanitation solutions

The study reveals the overall benefit consists of direct and indirect benefits from the environmental and social aspects presented in Figure 5 and Table 13. The estimated direct and indirect (co-benefit) social benefit is 77% and 70% indicates the satisfactory level of benefits from the implemented adaptive water and sanitation solutions. This is because enjoying available pure drinking water is a direct social benefit and getting more time for household take care is an indirect social benefit. On the other hand, due to the establishment of a rainwater harvesting plant as adaptive water and sanitation solution, the level of groundwater increases in the vulnerable areas, and this was reported by the FGD’s participants.

Figure 5. Percentage of the benefit of adaptive water and sanitation solutions

Table 13. Benefits of adaptive water and sanitation solutions

| Direct benefit | Co-benefit benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Decreased scarcity of pure drinking water | - | Can spend more time on housework due to save time | Increased sustainability of groundwater reservation |
| Decreased water-borne disease | - | Can spend more time for children education due to saving time |  |
|  | - | Children, adult and disabled person get more care from their household members |  |

Reduce loss and damage of life and property

In Figure 6 the study reveals the percentage distribution and in Table 14 the study reveals the items of benefit for the climate change adaptation category of reducing loss and damage of life and property. The estimated overall social benefit (91%) which covers the direct and indirect social benefits indicates a very satisfactory level of benefits. It is reported by the FGD participants that, due to providing safety equipment such as life jackets life risks become much more reduced for fishermen and passengers. Besides due to the implementation of lightening shed the death rate reduced tremendously than before. Now the community people use the lightening shed as flood and cyclone shelter. Therefore, their mental satisfaction is enriched than before.

Figure 6. Percentage of the benefit of reduce loss and damage of life and property

Table 14. Benefits of reduce loss and damage of life and property

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Decreased life risk during fishing in bad weather | - | Can do agricultural work without fear | - |
| Increased mental satisfaction | - | Used as flood shelter | - |
| Women, children and the disabled can move without fear during bad weather | - |  | - |
| Decreased death rate from lightening | - |  | - |

Reduce impacts of flood and waterlogging

It is evident from Figure 7 that the indirect social benefit is higher than the direct social benefit. Due to the climate change adaptation measures such as a culvert, drain, village protection walls, guide wall, and flood protection the community people are now able to protect their houses and livestock from damage during the flush flood which is identified as a direct social benefit (Table 15). Also, students, children, adults, women, and the disabled enjoy an indirect social benefit from these climate change adaptation measures. On the other hand, the direct environmental benefit is higher than the indirect environmental benefit. Reducing waterlogging from agricultural land was identified as a direct environmental benefit whereas washing away garbage and reducing soil erosion was identified as an indirect environmental benefit in this study.

Figure 7. Percentage of the benefit of reduce impacts of flood and waterlogging

Table 15. Benefits of reduce impacts of flood and waterlogging

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Protected houses | Reduced waterlogging of agricultural land | Local people can easily go to the local market | Washed away garbage during excessive rain |
| Reduced crops damage |  | Easier for pregnancy women to go to local community clinic local community clinic | Reduce soil erosion |
| Reduced livestock damage |  | Students can easily go to school |  |
|  |  | Children, disabled, and old age safety is ensured |  |
|  |  | The drain is also used for irrigation in dry season |  |

Improve accessibility to flood shelter, cyclone shelter, kella, and water source

The study finds social and environmental benefits in the case of direct and indirect benefits for improving accessibility to flood shelter, cyclone shelter, and water sources (Figure 8 and Table 16). The study reveals a satisfactory level of direct social benefit and a very satisfactory level of indirect social benefit. The FGD participants said that it is easier and safe to go to cyclone shelters than before and identified this as a direct social benefit of bridge and road construction. Also, the construction of bridges and roads makes it easier to go to the local community clinic in the case of pregnant women which is identified as an indirect social benefit. Furthermore, the study finds reducing waterlogging and reducing soil erosion as direct environmental and indirect environmental benefits respectively.

Figure 8. Percentage of the benefit of Improve accessibility to flood shelter, cyclone shelter, kella, and water source

Table 16. Benefits of Improve accessibility to flood shelter, cyclone shelter, kella, and water source

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Easier and safe to go to cyclone shelter during cyclone | Reduced waterlogging of agricultural land | Students can easily go to school | Reduced soil erosion |
|  |  | Local people can easily go to the local market |  |
|  |  | Easier for pregnancy women to go to local community clinic local community clinic |  |
|  |  | Easier to move for children and disabled person |  |

Promote climate-resilient agriculture

The percentage distributions of benefits are presented in Figure 9 whereas the benefits items are presented in Table 17. From Figure 8, it is seen that both direct and indirect social benefit is good while the both direct and indirect environmental benefit is sufficiently good. The benefits of solar-powered ground-water and surface-water irrigation systems are comparatively higher than diesel-powered irrigation systems which indicates the direct social benefit. On the other hand, the sustainability of groundwater reservations which is identified as an indirect environmental benefit has enhanced due to the implication of solar-powered surface water irrigation systems.

Figure 9. Percentage of the benefit of promote climate-resilient agriculture

Table 17. Benefits of promote climate-resilient agriculture

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Enhanced knowledge on agriculture farming | Re-digging of canals has alleviated the shortage of water for plant & agriculture | Women use canals water for bath | Reduced carbon emission |
| The benefits of solar-powered ground-water irrigation systems are comparatively higher than diesel-powered irrigation systems |  | Flush floodwaters move quickly through canals | Increased sustainability of groundwater reservation |
| Increased cropping pattern |  |  |  |
| The benefits of solar-powered surface-water irrigation systems are comparatively higher than diesel-powered irrigation systems |  |  |  |

Improve adaptive, absorptive, and anticipatory capacity

The study finds only direct and indirect social benefits which are presented in Figure 10 and Table 18. A higher perception score is found for direct social benefit than indirect social benefit. The estimated perception score indicates the sufficiently good status of direct social benefits such as medical equipment and regular check-up for pregnant women and sufficiently good also for indirect social benefits such as getting information through radio and television due to the solar-power distribution.

Figure 10. Percentage of the benefit of improve adaptive, absorptive, and anticipatory capacity

Table 18. Benefits of improve adaptive, absorptive, and anticipatory capacity

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Community people can sell their agricultural products easily during flush flood | - | Due to the provision of night lighting due to solar electricity, women's interest in handicrafts | - |
| Medical supplies are very effective for pregnant women | - | Children of the family have increased interest in education | - |
| Easy to regular checkups for a pregnant woman | - | Due to solar power, the tendency to use radio, television or mobile has increased. | - |
| Women can buy and sell freely in Shuhashini sales center | - | Due to solar power, one can easily get information about the disaster forecast through the use of radio or television | - |

Nature-based Solutions

A climate change adaptation measure namely swamp plantation was implemented under the nature-based solution category. Due to the implementation of such adaptation measures the vulnerable community enjoys not only social benefits but also enjoy environmental benefits in the case of direct and indirect benefits (Figure 11 and Table 19). It is promising that the direct social benefit such as protecting life, house, and livestock during cyclones and flush floods indicates the more pleasing level of benefit. On the other hand, the perception score from the aspect of direct and indirect environmental benefits reflects a very satisfactory level of benefits.

Figure 11. Percentage of the benefit of nature-based Solutions

Table 19. Benefits of nature-based solutionsbased Solutions

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Protects life, house, and goods during cyclones and flush flood | Reduce soil erosion | Can be used as fuel wood | Increase ecological balance |

Climate resilient livestock solution

Climate resilient livestock solution that covers hydroponics which was implemented as a climate change adaptation measure provides direct and indirect benefits from the point of social and environmental aspects (Figure 12 and Table 20). The study reveals a higher pleasant level for direct and indirect social benefit and reveals a pleasant level for indirect benefit. The people of the vulnerable area cultivate hydroponics to ensure the availability of grass during the flush flood which is identified as a direct social benefit. Besides, such adaptation measure provides balance in the ecosystem by reducing carbon emission from the environment which is identified as an indirect environmental benefit.

Figure 12. Percentage of the benefit of climate resilient livestock solution

Table 20. Benefits of climate resilient livestock solution

| Direct benefit | Co-benefit |
| --- | --- |
| Social | Environmental | Social | Environmental |
| Increased availability of livestock fodder during floods | Balanced ecosystem | Women and disabled cultivate hydroponics at their homestead area for other purpose | - |

# KII participant’s perception on the performance assessment of the project

Level of perception index on project’s performance

To evaluate the performance of the project the study team has obtained the perception of DCFC, DDLG, UNO, and the Union chairman which is shown in Figure 13 and Table 21. The estimated score (82.9%) implies the project is at a very satisfactory level to meet the climate change issues which is reported by DCFC. Besides, a satisfactory level is identified in the case of DDLG, UNO, and Union chairman. On the other hand, all estimated perception scores are higher than 80% indicating a higher satisfaction level for the benefits which are extracted from the project's implemented climate change adaptation schemes. Furthermore, the overall perception score is 82.72% which lies between the threshold points of 80% to 100% implying a sufficiently good status of the project. Therefore, it can be said that the overall performance of the project is at a very satisfactory level.

Figure 13. Stakeholders’ perception (%) on the project performance

Table 21. Overall performance perception of stakeholders’ regarding the project

| Perception items | DCFC | DDLG | Union Chairman | UNO | Overall performance |
| --- | --- | --- | --- | --- | --- |
| How much benefited the vulnerable people from this project? | Very satisfactory | Very satisfactory | Very satisfactory | Very satisfactory | Very satisfactory |
| To what extent this project has solved climate change issues? | Very satisfactory | Satisfactory | Satisfactory | Satisfactory | Satisfactory |
| Overall performance | Very satisfactory | Very satisfactory | Very satisfactory | Satisfactory | Very satisfactory |

SWOT analysis of the project (Based on KII participant’s perceptions)

The study also performed the SWOT (Figure 14) analysis to see the strengths, weaknesses, opportunities, and threats of the project which are given as follows:

Strength:

The study identifies several strengths of the project. Strong coordination among the project’s staff and local government bodies is identified as the main strength which is reported by the KII participants. The Upazila facilitator, Upazila line department, District Climate Risk & Adaptation monitor (DCRAM), District Climate Finance coordinator, Deputy Director-Local Government (DDLG), Upazila Nirbahi Officer (UNO), Community Mobilization Facilitators (CMF), Union chairman, Ward member, and others are involved intimately in the project. Further, the KII participant reports a strong backward linkage in receiving co-finance from other sources. The study also found a good communication system between the local staff to the local community where the climate change adaptation measures were taken.

Weakness:

The study identifies some weaknesses along with strengths. Most of the KII participants mentioned the budget limitation of the project for some vulnerable areas like flush flood-prone zone namely Sunamganj. Besides, the participants think a long-term project is very effective than a short-term project for the climate-vulnerable community to mitigate and adapt the climate issues.

Opportunities:

The success of any project also depends on its opportunities. In the case of this impact evaluation, the study finds some opportunities which are identified by the DCFC, DDLG, UNO, and Union chairman. Environment awareness-raising program, building a 'Quick Response Team' in the local vulnerable areas so that they can help in the emergency case, skill development program for quick adaptation to natural disasters, providing a GPRS tracking system for fishermen, and providing salt and flood-tolerant agricultural seeds can be implemented by the project further to cope with the climate vulnerable issues.

Threats:

The study also finds some threats that may hamper the project's smoothness in the case of success. Hostile or harsh weather, higher cost of supplies or materials, and local leader can reduce the sustainability of the project.

Since the infrastructures are operating in relatively climate-vulnerable areas/regions periodic monitoring of them is required and if needed periodic maintenance should also be ensured for wider and sustainable use of these infrastructures.

Figure 14. SWOT analysis of the Project

# Conclusion and Policy Recommendation

Climate change is a global concern that has negative consequences, particularly in developing/emerging countries like Bangladesh. To mitigate the negative consequence of changing climate several initiatives were taken for the vulnerable community in different vulnerable areas of Bangladesh by the multi-donor collaborative of GoB, UNDP, UNCDF, EU, and SIDA. Therefore, this study aims to assess the impact of such initiatives on the local vulnerable people in 44 unions of 18 Upazila under 7 districts in Bangladesh. The study identified several types of co-benefit along with the direct benefits from each of the implemented climate change adaptation categories. From the aspect of quantitative assessment, it is found that the overall benefit is 62% while the overall co-benefit is 38%. The overall BCR is positive indicating better investment in the project. Considering total benefit, the highest BCR is found for adaptive water and sanitation solutions and improved accessibility to flood shelter, cyclone shelter, kella, and water source among all climate change adaptation categories.	 The study also finds higher co-benefit than the benefit for adaptive water and sanitation solutions and climate-resilient livestock solutions.

On the other hand, in the case of qualitative assessment, the study finds a highly pleasant level of satisfaction for social benefits and a pleasant level of satisfaction for environmental benefits which were extracted from the implemented climate change adaptation measures. Furthermore, the study finds a highly satisfactory level of performance in solving climate-related issues in the climate-vulnerable areas of Bangladesh that are reported by the KII participants of this study. Therefore, the study advocates for the implementation of more climate change adaptation schemes so that the people of climate-vulnerable areas can easily maintain their way of life.

# Footnotes

The term “programme” is used for programmes, joint programmes and projects.

Strategic Results, as formulated in the Strategic UN Planning Framework (e.g. UNDAF) or project document;

The MPTF Office Project Reference Number is the same number as the one on the Notification message. It is also referred to as “Project ID” on the project’s factsheet page the MPTF Office GATEWAY

The start date is the date of the first transfer of the funds from the MPTF Office as Administrative Agent. Transfer date is available on the MPTF Office GATEWAY

As per approval of the original project document by the relevant decision-making body/Steering Committee.

If there has been an extension, then the revised, approved end date should be reflected here. If there has been no extension approved, then the current end date is the same as the original end date. The end date is the same as the operational closure date which is when all activities for which a Participating Organization is responsible under an approved MPTF / JP have been completed. As per the MOU, agencies are to notify the MPTF Office when a programme completes its operational activities.

Note: Outcomes, outputs, indicators and targets should be as outlined in the Project Document so that you report on your actual achievements against planned targets. Add rows as required for Outcome 2, 3 etc.

Scale:

1.Specific commitment to finance local adaptation mentioned

2.Allocations made to finance local adaptation mentioned

3.Specific commitment to finance local adaptation mentioned

4.Allocations made to finance local adaptation mentioned

Polytomous variable means a variable having more than two possible, ordered or unordered categories.

The BCR values refer in this study should be considered as the least value since some of the benefits and co-benefits of the intervention schemes could be not quantified.

# Text boxes

LoGIC Climate Financing Model: CRF

LoGIC Climate Financing Model: PBCRG

From the support of this project, my mother has gained not just financial independence but also a sustainable way of life, breaking away from climate calamities. says 17-year-old Jayeda, daughter of speech impaired 44-year-old Dulia, residing in the climate-prone Taltoli Upazila of Barguna.

Feedback Received

III) Indicator Based Performance Assessment

Bazlul Khondker, PhD

October 27, 2022

Cost-benefit Analysis of PBCRG Funded Schemes of

Local Government Initiative on Climate Change (LoGIC) Project

Final Report

Figure 1. Flow chart of sampling

BOX 1

Decision rules (BCR)

- Based on direct and total benefit: if BCR > 1, accept the project; If BCR = 1, remain indifferent; and If BCR < 1, reject the project.

- Based on co-benefit: in the case of measuring co-benefit, the study considered the cost/investment which was used also for measuring direct and total benefits. Because, there was no cost/investment allocated separately for measuring co-benefits.  So any positive BCR (>0) indicates the project selection is right.

BOX 2

Benefit and Co-Benefit List: Adaptive Water and Sanitation Solutions

Direct benefit item

- Reduce expenditure for searching pure water

- Reduce expenditure on health treatment

Co-benefit item

- Increase income due to saving time

BOX 3

Benefit and Co-Benefit List: Reduce Loss and Damage of Life and Property

Direct benefit item

- Reduce expenditure on safety equipment

- Reduce financial loss by protecting the livestock during lightening

Co-benefit item

- Increase income by fishing more with safety

- Increase income by wage earning

BOX 4

Benefit and Co-Benefit List: Reduce Impacts of Flood and Waterlogging

Direct benefit item

- Reduce financial loss from crop damage

- Reduce financial loss by protecting household wealth damage

- Income increase due to higher crops production

- Reduce financial loss from aquaculture damage

- Reduce transportation cost

Co-benefit item

- Increase income by wage earning

BOX 5

Benefit and Co-Benefit List: Improve Accessibility to Flood Shelter, Cyclone Shelter, Kella, and Water Source

Direct benefit item

- Income increase due to higher crops production

- Reduce financial loss from crop damage

- Reduce financial loss from aquaculture damage

- Reduce transportation cost

Co-benefit item

- Increase income by wage earning

BOX 6

Benefit and Co-Benefit List: Promote Climate Resilient Agriculture

Direct benefit item

- Increase income from crops

- Reduced expenditure on diesel cost

Co-benefit item

- Increase income by fishing

- Increase income by wage earning

- Reduce financial loss by participation in training program

- Income increases by exchanging water from pond for aquaculture

BOX 7

Benefit and Co-Benefit List: Improve Adaptive, Absorptive, and Anticipatory Capacity

Direct benefit item

- Increase income by selling agricultural crops

- Decrease expenditure on fuel such as diesel, kerosine, and etc.

- Reduced expenditure on childbirth

Co-benefit item

- Decrease financial loss from crops

- Increase income (such as handicrafts and other IGAs)

- Decrease expenditure on other health costs

BOX 8

Benefit and Co-Benefit List: Climate Resilient Livestock Solution

Direct benefit item

- Increase milk production

Co-benefit item

- Decrease feed cost

BOX 9

A decision Rule on Perception Score: By Polemi (2018)

Very satisfactory= values≥80%, Satisfactory= values between ≥60% and <80%, Neutral= values between ≥40% and <60%, Less satisfactory= values between ≥20% and <40%, and Very less satisfactory=1% to <20%.